NOVO LIFE

MES PAS-X Lifecycle Package

IT IMPLEMENTATION REPORT

NL-MES-IREP-001

DOCUMENT CLASSIFICATION

DUMMY / SIMULATED - Fictional implementation-stage report for hackathon/audit training. No production deployment, live data, real supplier reliance, residual-risk acceptance, release for use, operational handover or validated-state conclusion is represented.

| Control field | Value |
| --- | --- |
| Document title | IT Implementation Report |
| Document ID | NL-MES-IREP-001 |
| Version / date | 0.1 / 11 Aug 2026 |
| Project / solution | Novo Life MES PAS-X New Implementation / fictional GxP-critical context |
| Plan reported | NL-MES-IPLAN-001 v0.1 |
| Status | Simulated Reviewed and Approved for Demo/Training Use Only. |
| Source baseline | 22 controlled DUMMY DOCX files; this report becomes sequence 23 |
| Delivered register | 23 of 29 issued including this report; 6 downstream deliverables Open |
| Verification | IQ and recovery verification successful (simulated); OV/PfV/UAT and production verification not performed |
| Risks | 26 Open; 0 residual ratings; 0 accepted |
| Overall decision | IMPLEMENTATION REPORT ACCEPTED; RELEASE FOR PRODUCTION/USE AND HANDOVER NOT AUTHORISED |

CONTROLLED STATUS

Simulated Reviewed and Approved for Demo/Training Use Only. Approval confirms that this report faithfully reconciles the DUMMY plan and available evidence. It is not approval of production deployment, intended-use fitness, risk acceptance, release or handover.

Dummy document created for hackathon/training simulation only. Not valid for operational, regulatory, inspection, or GxP release use.

# Document lifecycle and simulated approvals

| Lifecycle object | Role | Approval purpose | Status | Effect |
| --- | --- | --- | --- | --- |
| Implementation plan | IT Solution / Project Manager | Strategy, activities, deliverables and responsibilities | Final Approved (simulated) | Plan baseline frozen in NL-MES-IPLAN-001 |
| Implementation plan | IT System Owner / QA | Scope, risk-based lifecycle and quality oversight | Final Approved (simulated) | Authorised DUMMY planning baseline only |
| Implementation report | Fictional Report Author | Evidence reconciliation, variances and unresolved items | Final Approved (simulated) | This report |
| Implementation report | IT System Owner | Accuracy, ownership and release boundary | Final Approved (simulated) | No release authorised |
| Implementation report | Quality Assurance | GxP/evidence oversight and conclusion | Final Approved (simulated) | No validated-state or release conclusion |

| Version | Date | Author role | Change summary |
| --- | --- | --- | --- |
| 0.1 | 11 Aug 2026 | Fictional Implementation Report Author | Initial DUMMY implementation report; reports NL-MES-IPLAN-001 outcomes, changes, unresolved items and release decision without modifying the plan. |

SIGNATURE BOUNDARY

Real electronic identities, initials and signatures are intentionally omitted. Approval entries are fictional role records with no operational or regulatory effect.

# Executive implementation conclusion

OVERALL IMPLEMENTATION DECISION

REPORT ACCEPTED / RELEASE NOT AUTHORISED. The 22-document source baseline and this IREP demonstrate a coherent DUMMY lifecycle through approved requirements/design, simulated IQ, backup/restore verification and an isolated recovery exercise. They do not demonstrate full intended-use verification, production deployment, residual-risk acceptance, operational readiness or handover.

| Decision area | Reported evidence | Conclusion | Release implication |
| --- | --- | --- | --- |
| Planning and design | MLGP, SYS, IPLAN, URS, risk assessments, specifications, DIA, DRR and TRM | Complete for controlled DUMMY baseline | Permits only scoped simulated progression |
| Installation verification | 32/32 cases and 224/224 final accepted steps Passed after closed exceptions | Successful (simulated) | Does not replace OV/PfV/UAT or production verification |
| Continuity/recovery | BRVR 12/12; IRTR 12/12 runs, 40/40 steps, 20/20 checks, 10/10 criteria | Successful (simulated) | Does not establish operational readiness |
| Exceptions/findings | 8 defects + 6 deviations closed; 9 design-gate findings closed; 1 handoff finding Open | No unresolved executed-IQ exception; one lifecycle action Open | Handover remains blocked |
| Risk | 26 risks Open; no residual rating or acceptance | Not ready | G5 cannot be approved |
| Operations/release | OMSOP, UG, AG, SLA, TRN and VSR not issued; no production activity | Not ready | No production release, release for use or handover |

| Population | Planned / controlled | Reported state | Conclusion |
| --- | --- | --- | --- |
| Lifecycle deliverables | 29 | 23 issued including IREP; 6 Open | Partial |
| Implementation activities | 35 | 25 Complete/scoped; 10 Open/not performed/deferred | Partial |
| Gates | G0-G6 | 2 Met; 2 Scoped Met; 3 Not Met | G5/G6 unavailable |
| Requirements/design trace | 50 URS/FS/DS/CI; 60 integration | Structural trace retained | Verification completion not inferred |
| Risks | 26 | 26 Open; 0 accepted | Not release-ready |
| Plan Verify items | 18 | 1 closed for DUMMY; 10 partial; 7 Open | Open actions retained |

# 1 Purpose

This IT Implementation Report records the executed status of the implementation strategy, activities, deliverables and responsibilities defined in NL-MES-IPLAN-001 for the fictional Novo Life MES PAS-X implementation. It updates final DUMMY deliverable versions, reports material differences from the approved plan, reconciles evidence and exceptions, identifies unresolved items, and provides an explicit readiness decision.

The report follows Q0359350 by keeping the approved plan unchanged. Reported results and variances are contained here. The report is approved within the simulation because its evidence and boundaries are internally consistent; approval does not mean that the solution is fit for intended use or released.

# 2 Document lifecycle and scope

## 2.1 Plan-to-report lifecycle

| Controlled record | Version | Purpose | State | Relationship |
| --- | --- | --- | --- | --- |
| NL-MES-IPLAN-001 | 0.1 | Prospective implementation strategy and plan | Final Approved (simulated) | Frozen source; not rewritten |
| NL-MES-IREP-001 | 0.1 | Retrospective activity, evidence, variance and conclusion report | Simulated Reviewed and Approved for Demo/Training Use Only. | Reports actual DUMMY state |
| NL-MES-VSR-001 | No approved version | Final validation/release recommendation | Open / not issued | Must use this IREP plus remaining evidence |

## 2.2 Included and excluded scope

| Included | Excluded / not represented |
| --- | --- |
| All 22 prior controlled DUMMY lifecycle DOCX files plus this IREP | Any live QMS, ServiceNow, TIMS, supplier, quality or release record |
| Seven planned phases, seven gates, 35 activities and 29 deliverables | Activities/evidence not present in the controlled DUMMY package |
| Requirements/design/trace, IQ, backup/restore and recovery exercise evidence | OV, PfV, UAT, pIV, pPfV or actual production execution |
| Simulated approvals, closed IQ exceptions and explicit open actions | Real names, signatures, contacts, credentials, endpoints, product/batch/patient/personal data |
| Evidence-based decision to defer release and handover | Release for production, release for use, validated state or operational handover |

## 2.3 Reporting cut-off

The reporting cut-off is 11 Aug 2026. The baseline contains exactly 22 pre-existing controlled DOCX files. NL-MES-IREP-001 is sequence 23 and is included in the reported 23-of-29 deliverable count. Later artifacts must update their own controlled records; they must not be inferred as complete from this IREP.

# 3 Project and system summary

| Field | Reported value |
| --- | --- |
| Project | Novo Life MES PAS-X New Implementation |
| Change reference | DUMMY-CHG-MES-001 planning placeholder only; no real change record |
| Business impact | GxP: Yes (working); confidentiality/integrity/availability criticality retained; financial and personal-data applicability Verify |
| Process scope | Seven fictional manufacturing, recipe, execution, LIMS, review, reporting and administration process areas |
| Component scope | PAS-X application/database/integration/reporting plus IAM, time, backup and monitoring services |
| Environment scope | Conceptual DEV/TEST/VAL/PROD/DR; executed DUMMY verification only in isolated TEST/VAL simulation |
| Software category | Configured application category 4 working basis; category 5 only if custom code exists; authoritative inventory Open |
| Data migration | No legacy migration assumed; initial-load applicability remains Verify |

# 4 Roles and responsibilities

| Role | Implementation-report responsibility | Reported accountability |
| --- | --- | --- |
| Business Process Owner | Confirms intended-use/business readiness and unresolved business actions | No release approval in this report |
| IT System / Solution Owner | Accountable for scope, risk decisions, supplier/service readiness and release boundary | Approves report; residual risk acceptance remains pending |
| IT Project / Solution Manager | Reconciles plan, activities, evidence, deliverables, changes and actions | Report owner in simulation |
| Validation Lead | Evaluates lifecycle/verification completeness and traceability | Confirms partial verification state |
| Quality Assurance | Provides GxP oversight and approves truthful report conclusion | Does not approve release or validated state |
| Technical / Integration Lead | Confirms design, installation, interface and infrastructure evidence | Real product/PROD/interface evidence actions remain open |
| Data Integrity / Security SME | Reviews data, access, signature, audit, continuity and security control evidence | Operating controls and residual decisions remain open |
| Test Manager / Reviewer | Reports IQ/recovery runs, exceptions, reruns, baselines and acceptance | Executed DUMMY scope accepted |
| Supplier / Service Provider | Provides product/QMS/security/lifecycle/service evidence | No real supplier evidence accepted |
| Training Coordinator / Operations | Completes operational training, procedures, support and handover | Not complete |

# 5 Reporting on planned implementation activities

## 5.1 Phase status

| Phase | Planned stage | Plan timing | Reported state | Evidence / unresolved boundary | Controlled reference |
| --- | --- | --- | --- | --- | --- |
| P0 | Mobilise | W01-W02 illustrative | Complete (simulated) | Scope, lifecycle, roles, repositories and G0 baseline established | MLGP / SYS / IPLAN |
| P1 | Requirements and risk | W03-W08 illustrative | Complete - planning baseline | 50 URS, ITRA, ITRRA and supplier assessment issued; residual decisions remain open | URS / ITRA / ITRRA / SUPA |
| P2 | Design | W07-W14 illustrative | Complete - scoped design baseline | FS/IS/DS/CS/DIA/DRR/TRM issued; 9 IQ-gate findings later closed, 1 handoff finding open | FS / IS / DS / CS / DIA / DRR / TRM / IQR |
| P3 | Build and configure | W11-W20 illustrative | Partial | Controlled DUMMY configuration/IQ baseline established; real supplier/development/custom-object evidence not concluded | CS / IQP / IQTC / IQR / SUPA |
| P4 | Acceptance verification | W18-W26 illustrative | Partial | IQ and recovery verification completed; OV/PfV/UAT and production verification not performed | IQR / BRVR / IRTR |
| P5 | Deploy and hand over | W25-W30 illustrative | Not completed | No actual production deployment; operational documents, SLA, training and handover remain open | IREP open-action register |
| P6 | Report and recommend | W30-W32 illustrative | Partial | IREP and unresolved-item reporting complete; residual-risk acceptance, VSR and release recommendation deferred | IREP / future VSR |

## 5.2 Detailed activity result

| Activity | Phase | Planned implementation activity | Reported status | Evidence / disposition |
| --- | --- | --- | --- | --- |
| IPA-IREP-001 | P0 | Approve DUMMY lifecycle scope and document sequence | Complete (simulated) | NL-MES-MLGP-001 |
| IPA-IREP-002 | P0 | Establish system boundary and intended-use context | Complete (simulated) | NL-MES-SYS-001 |
| IPA-IREP-003 | P0 | Approve implementation strategy, roles and dependencies | Complete (simulated) | NL-MES-IPLAN-001 |
| IPA-IREP-004 | P0 | Define document/change/defect/deviation routes | Complete (simulated) | IPLAN / DEFL / DEVL |
| IPA-IREP-005 | P0 | Record G0 planning baseline | Complete (simulated) | IPLAN / MLGP |
| IPA-IREP-006 | P1 | Approve 50-requirement URS baseline | Complete (simulated) | NL-MES-URS-001 |
| IPA-IREP-007 | P1 | Complete gross-risk and lifecycle-control assessment | Complete - baseline only | NL-MES-ITRA-001; 26 risks Open |
| IPA-IREP-008 | P1 | Complete requirement-level risk assessment | Complete - baseline only | NL-MES-ITRRA-001 |
| IPA-IREP-009 | P1 | Assess supplier and service dependence | Complete - conditional | NL-MES-SUPA-001; GxP delivery blocked |
| IPA-IREP-010 | P1 | Record G1 requirements/risk baseline | Complete (simulated) | URS / ITRA / ITRRA / SUPA |
| IPA-IREP-011 | P2 | Approve functional design for all 50 requirements | Complete (simulated) | NL-MES-FS-001 |
| IPA-IREP-012 | P2 | Approve 60 integration requirements and design controls | Complete (simulated) | NL-MES-IS-001 |
| IPA-IREP-013 | P2 | Approve technical and configuration design baselines | Complete (simulated) | NL-MES-DS-001 / CS-001 |
| IPA-IREP-014 | P2 | Complete data-integrity assessment and final design review | Complete - conditional | NL-MES-DIA-001 / DRR-001 |
| IPA-IREP-015 | P2 | Establish bidirectional trace baseline | Complete - planning baseline | NL-MES-TRM-001 |
| IPA-IREP-016 | P3 | Establish controlled DUMMY configuration/installation baseline | Complete (simulated) | CS / IQP / IQTC / IQR |
| IPA-IREP-017 | P3 | Obtain real supplier development, product and custom-object evidence | Open | SUPA conditions; VER-IPLAN-001/007/008 |
| IPA-IREP-018 | P3 | Approve IQ protocol and 32 test cases | Complete (simulated) | NL-MES-IQP-001 / IQTC-001 |
| IPA-IREP-019 | P3 | Operate defect and validation-deviation controls | Complete (simulated) | 8 defects + 6 deviations closed |
| IPA-IREP-020 | P3 | Close IQ activation findings and readiness gates | Complete - scoped | 9 gate findings closed; DUMMY-DRF-MES-007 open/non-gate |
| IPA-IREP-021 | P4 | Execute and report installation qualification | Complete (simulated) | 32/32 cases; 224/224 final accepted steps Passed |
| IPA-IREP-022 | P4 | Verify backup and restore capability | Complete (simulated) | NL-MES-BRVR-001; 12/12 activities Passed |
| IPA-IREP-023 | P4 | Approve recovery plan and execute recovery exercise | Complete (simulated) | IRP / IRTR; all objectives and criteria Met |
| IPA-IREP-024 | P4 | Execute OV/PfV/UAT or equivalent intended-use verification | Not performed / Open | No approved report in baseline |
| IPA-IREP-025 | P4 | Execute production IV/PfV and final production baseline | Not performed / Open | No production activity represented |
| IPA-IREP-026 | P5 | Perform simulated deployment/handover readiness review | Complete - assessment only | IREP phase/gate and action registers |
| IPA-IREP-027 | P5 | Deploy to production and approve cutover/rollback evidence | Not performed | No production deployment |
| IPA-IREP-028 | P5 | Approve O&M SOP, user/admin guides and SLA | Open | NL-MES-OMSOP/UG/AG/SLA not issued |
| IPA-IREP-029 | P5 | Complete role-based operational and end-user training | Open | NL-MES-TRN-001 not issued |
| IPA-IREP-030 | P5 | Complete ownership, support and knowledge-transfer handover | Open | G6 prerequisites incomplete |
| IPA-IREP-031 | P6 | Issue implementation report | Complete (simulated) | NL-MES-IREP-001 |
| IPA-IREP-032 | P6 | Report plan variances and unresolved items | Complete (simulated) | IREP Sections 10-11 |
| IPA-IREP-033 | P6 | Rate and accept residual risks | Open | 26 risks Open; 0 accepted |
| IPA-IREP-034 | P6 | Issue VSR and final release recommendation | Deferred | NL-MES-VSR-001 not issued |
| IPA-IREP-035 | P6 | Approve G5 release readiness and G6 handover | Not Met | Release/handover prohibited by this report |

STATUS INTERPRETATION

Activity completion is scoped: 'Complete' means the corresponding DUMMY planning or execution record is complete. It does not convert unperformed production, intended-use, risk-acceptance, operational or handover activities into completed work.

## 5.3 Gate evaluation

| Gate | Decision | Reported result | Evidence basis | Permitted progression / boundary |
| --- | --- | --- | --- | --- |
| G0 | Plan baseline | Met (simulated) | MLGP, SYS and IPLAN approved | Progress to requirements/risk baseline only |
| G1 | Requirements and risk baseline | Met (simulated) | 50 URS; ITRA/ITRRA/SUPA issued | Risk treatment/effectiveness/residual acceptance remain later activities |
| G2 | Design readiness | Scoped Met | FS/IS/DS/CS/DIA/DRR/TRM; 9 gate findings closed before IQ | Supports DUMMY IQ progression; not final production/readiness conclusion |
| G3 | Verification readiness | Scoped Met | IQ/recovery plans, cases, baselines and exception controls activated | Applies only to executed IQ/BRVR/IRTR scope |
| G4 | Deployment readiness | Not Met | OV/PfV/UAT, production verification and cutover evidence absent | Do not deploy to production |
| G5 | Release readiness | Not Met | 26 risks Open; VSR and operational package absent | Do not release for production or use |
| G6 | Handover | Not Met | OMSOP/UG/AG/SLA/TRN and ownership transfer absent | Do not hand over to operations |

GATE BOUNDARY

G4, G5 and G6 are Not Met. No reader may infer production deployment, release for use or operational handover from the simulated approvals on this report or its source documents.

# 6 Reporting on assessments, design and development

## 6.1 Assessment results

| Assessment | Controlled record | Reported outcome | Release implication |
| --- | --- | --- | --- |
| IT risk assessment | NL-MES-ITRA-001 | 26 risks identified; working levels retained; no residual ratings | Not accepted for release |
| Requirement risk assessment | NL-MES-ITRRA-001 | 50 requirements and verification rigor mapped | Supports planning; effectiveness incomplete |
| Supplier assessment | NL-MES-SUPA-001 | Conditionally fit for selection/planning only | Qualification/agreement/evidence gates block GxP delivery |
| Data integrity assessment | NL-MES-DIA-001 | Data lifecycle and controls defined; authoritative data/retention/migration values Verify | Operating evidence required |
| Business process impact | IPLAN / ITRA | GxP Yes working; confidentiality/integrity/availability critical | Conservative full lifecycle retained |
| Software category | IPLAN / SUPA / DRR | Category 4 working basis; category 5 if custom objects exist | Custom-object inventory action remains Open |

## 6.2 Design and development conclusion

| Area | Evidence | Reported conclusion | Open boundary |
| --- | --- | --- | --- |
| Functional design | 50 URS-to-FS links | Structurally complete and approved in DUMMY baseline | Intended-use verification not complete |
| Integration design | 60 integration requirements | Design coverage established | Actual contracts/values and end-to-end tests Open |
| Technical/configuration design | 50 DS/CI links | Supports scoped simulated IQ | Actual product/build/custom-object baseline Open |
| Final design review | 10 findings / PV-G1..G5 | 9 gate-linked findings closed before IQ; 1 handoff finding Open | Not a final operational readiness conclusion |
| Development verification | IQ configuration/installation evidence | Configuration/installation state verified in simulation | Supplier unit/system/code evidence not concluded |
| Traceability | 50 URS/FS/DS/CI; 60 INT; 26 risks | Structural trace retained | OV/PfV/UAT/result/residual-risk trace incomplete |

# 7 Reporting on verification, baselines and exceptions

## 7.1 Verification result

| Verification area | Planned / executed population | Reported result | Conclusion | Boundary |
| --- | --- | --- | --- | --- |
| Installation qualification | 32 cases / 224 original steps | 32/32 cases Passed; final accepted 224/224 steps Passed | Successful (simulated) | TEST/VAL DUMMY only |
| IQ defects | 8 | 8 closed; 8 targeted reruns Passed | Resolved (simulated) | No open IQ defect |
| IQ validation deviations | 6 | 6 closed; 6 targeted reruns Passed | Resolved (simulated) | No residual IQ validity impact |
| Backup/restore verification | 12 planned activities | 12/12 Passed | Successful (simulated) | Supports recovery planning only |
| Recovery test | 12 runs / 40 steps / 20 checks / 10 criteria | All Passed/Met; RPO/RTO/WRT/MTD within targets | Successful (simulated) | Isolated exercise only |
| OV/PfV/UAT | Risk-based intended-use suite | Not performed / no approved report | Not concluded | Blocks G4/G5 |
| pIV/pPfV | Production verification and final baseline | Not performed | Not concluded | No production release |

## 7.2 Baseline and environment conclusion

| Baseline domain | Reported state | Conclusion |
| --- | --- | --- |
| Requirements/design/trace | Approved DUMMY versions 0.1; exact 50/50/50/50 and 60/26 populations | Controlled for this report |
| IQ installation/configuration | Five IQ baselines established; differences linked to closed exceptions | Accepted for simulated IQ |
| Recovery | Six IRTR baseline domains compared; differences accounted | Accepted for isolated recovery exercise |
| Production | No actual production baseline or comparability evidence | Not established |
| Document package | 22 pre-existing source hashes reconciled; no source modified | Controlled source baseline |

## 7.3 Exception and finding reconciliation

| Record class | Population | Closed | Open | Reported implication |
| --- | --- | --- | --- | --- |
| IQ defects | 8 | 8 | 0 | All corrections and reruns accepted (simulated) |
| Validation deviations | 6 | 6 | 0 | All validity implications resolved (simulated) |
| Design-review findings | 10 | 9 | 1 | DUMMY-DRF-MES-007 blocks operational handover, not scoped IQ |
| IRTR execution exceptions | 0 | 0 | 0 | No defect, deviation, rerun or protocol change |
| Plan-to-report variances | 10 | 10 reported | 0 hidden | All retained in Section 10 |

# 8 Deliverables and supporting processes

## 8.1 Deliverable completion summary

| Measure | Count | Reported state |
| --- | --- | --- |
| Planned lifecycle deliverables | 29 | Complete register in Appendix A |
| Issued before IREP | 22 | All controlled DOCX v0.1 / Final Approved (simulated) |
| IREP | 1 | This report / Final Approved (simulated) |
| Issued including IREP | 23 | 23/29 |
| Downstream Open | 6 | OMSOP, UG, AG, SLA, TRN, VSR |

## 8.2 Supplier and infrastructure deliverables

| Deliverable area | Reported state | Evidence / gap | Conclusion |
| --- | --- | --- | --- |
| Supplier QMS and lifecycle evidence | Open | No real supplier response/audit/SOC evidence | Not relied on for release |
| Product release/compatibility/known issues | Open | Exact release/modules/product support Verify | G4 blocked |
| Security/vulnerability/patch evidence | Open | Supplier/security evidence gate | Residual risk cannot be accepted |
| Service/support/change/incident obligations | Open | Agreement and SLA not approved | Operations/handover blocked |
| Infrastructure specification/baseline | Partial | Conceptual DS/CS and simulated IQ only | Actual production baseline absent |
| Backup/recovery evidence | Complete for DUMMY | BRVR/IRP/IRTR accepted in simulation | Operational cadence/ownership still open |

## 8.3 Supporting-process status

| Process | Reported state | Evidence | Open need |
| --- | --- | --- | --- |
| Change management | Defined for DUMMY lifecycle | IPLAN / exception/change records | Real release/change record |
| Defect management | Executed and closed | DEFL / IQR | Operational integration later |
| Validation-deviation management | Executed and closed | DEVL / IQR | Operational process later |
| Configuration management | Established for DUMMY IQ/recovery | CS / IQ / IRTR baselines | Production baseline/comparability |
| Supplier management | Conditional assessment only | SUPA | Qualification/evidence/agreements |
| Security/data integrity | Designed and partly verified | ITRA / DIA / design / IQ | Operating controls/residual decision |
| Backup/recovery | Verified in isolated simulation | BRVR / IRP / IRTR | Operational ownership/cadence |
| Document management | Controlled DUMMY package | Source hashes and approval records | Real QMS repositories/workflows |
| Training/readiness | Implementation roles simulated; operations incomplete | IQ/IRTR role records | TRN and handover |

# 9 Training, operations and handover

| Readiness domain | Planned output | Reported state | Decision |
| --- | --- | --- | --- |
| Implementation/technical roles | Qualified project/configuration/test personnel | Represented by fictional role qualification in controlled DUMMY records | Complete for simulation only |
| Testers/reviewers | Execution and documentation qualification | Represented in IQ/BRVR/IRTR records | Complete for simulation only |
| MES users/supervisors | Approved user guide and role training | UG/TRN not issued | Not ready |
| Administrators/support | AG/OMSOP/SLA and support qualification | AG/OMSOP/SLA/TRN not issued | Not ready |
| Owners/QA | Ownership, periodic review, risk and maintained-state training | Handover evidence absent | Not ready |
| Hypercare/knowledge transfer | Agreed handover criteria and support period | Not defined | Not ready |

HANDOVER ACTION

DUMMY-DRF-MES-007 remains Open. The handover checklist cannot be concluded until the operational instructions, manuals, service commitments, training, ownership and knowledge-transfer evidence are approved.

# 10 Changes from the approved implementation plan

The following table reports changes, outcomes and variances against NL-MES-IPLAN-001. None of these entries changes the approved plan text. Each difference is explicitly dispositioned in this report, as required by Q0359350.

| Change | Plan section / topic | Approved plan | Reported implementation state | Disposition |
| --- | --- | --- | --- | --- |
| CHG-IREP-001 | Document lifecycle | Separate IREP planned | Separate NL-MES-IREP-001 issued | No plan change; planned lifecycle applied |
| CHG-IREP-002 | Schedule | Illustrative W01-W32 | DUMMY records dated 10-11 Aug 2026 | Reported timing only; no real schedule claim |
| CHG-IREP-003 | Design readiness | DRR findings/gates to close before affected verification | 9 gate-linked findings closed before IQ; DUMMY-DRF-MES-007 remains Open | Scoped IQ progression accepted; handover still blocked |
| CHG-IREP-004 | Verification | IQ, interface/security, backup/recovery and UAT/process verification planned | IQ and recovery completed; OV/PfV/UAT and production verification not performed | Major scope/status variance; release deferred |
| CHG-IREP-005 | Environment/deployment | PROD deployment and limited production checks planned | Only isolated DUMMY TEST/VAL activity represented | Production deployment not executed or authorised |
| CHG-IREP-006 | Defect/deviation state | Controlled processes planned | 8 defects and 6 validation deviations closed after successful reruns | Execution outcomes reported; no unresolved verification exception |
| CHG-IREP-007 | Supplier evidence | Supplier deliverables to support implementation | Supplier remains conditionally fit for planning; qualification/agreement evidence open | GxP delivery/release blocked |
| CHG-IREP-008 | Risk acceptance | Controls verified and residual decisions before release | 26 risks remain Open; 0 residual ratings/acceptances | G5 cannot be met |
| CHG-IREP-009 | Operations/training | Procedures, SLA, training and support ready before G5/G6 | OMSOP/UG/AG/SLA/TRN not issued | Release and handover deferred |
| CHG-IREP-010 | Final recommendation | IREP/TRM/risk decisions feed VSR | IREP issued; VSR not issued | No final fit-for-use, validated-state or release conclusion |

MAJOR PLAN VARIANCE

The most material variance is deferral of the planned production/release endpoint. Only isolated DUMMY TEST/VAL evidence exists; full intended-use and production verification, operational readiness, residual-risk acceptance and release remain open.

# 11 Unresolved items and action plan

| Action | Required closure | Owner role | Due gate | Status | Trace |
| --- | --- | --- | --- | --- | --- |
| ACT-IREP-001 | Confirm exact PAS-X release, modules, product, custom-object inventory and supported deployment model. | IT Solution Owner / Supplier Representative | Before G4 | Open | VER-IPLAN-001/007; SUPA |
| ACT-IREP-002 | Complete supplier qualification, QMS/security evidence, responsibility split, agreements and service commitments. | IT Solution Owner / Supplier Manager | Before G4/G5 | Open | SUPA; VER-IPLAN-008 |
| ACT-IREP-003 | Approve actual environment/topology inventory, production baseline, comparability, capacity and monitoring thresholds. | Infrastructure / Security Lead | Before G4 | Open | VER-IPLAN-002/003/012 |
| ACT-IREP-004 | Approve actual interface contracts and execute end-to-end interface/security verification. | Integration / Security Lead | Before G4/G5 | Open | VER-IPLAN-004/005/010 |
| ACT-IREP-005 | Execute risk-based OV/PfV/UAT or equivalent intended-use verification and report results. | Verification Lead / Business Process Owner | Before G5 | Open | IPA-IREP-024 |
| ACT-IREP-006 | Approve cutover/rollback plan and execute pIV/pPfV plus final production baseline comparison. | Project / IT Solution Manager | Before G5 | Open | VER-IPLAN-014; IPA-IREP-025/027 |
| ACT-IREP-007 | Issue OMSOP, User Guide, Administrator Guide and SLA; close DUMMY-DRF-MES-007. | Operations Lead / IT Solution Owner | Before G5/G6 | Open | NL-MES-OMSOP/UG/AG/SLA; DUMMY-DRF-MES-007 |
| ACT-IREP-008 | Confirm migration/initial-load applicability and approve plan/report if applicable. | Data Owner / Validation Lead | Before G4/G5 | Open | VER-IPLAN-009/018; RSK-MES-026 |
| ACT-IREP-009 | Complete training package, role assignment, qualification evidence and operational knowledge transfer. | Training Coordinator / Operations Lead | Before G5/G6 | Open | NL-MES-TRN-001 |
| ACT-IREP-010 | Implement/evaluate all risk controls, rate residual risks and obtain authorised acceptance with QA involvement. | IT Solution Owner / QA | Before G5 | Open | RSK-MES-001..026 |
| ACT-IREP-011 | Resolve actual document repositories, approvals, release/change record and retention/access controls. | Document Owner / IT Solution Manager | Before G5 | Open | VER-IPLAN-015/017 |
| ACT-IREP-012 | Issue VSR, decide G5/G6, communicate authorised release if approved and complete handover acceptance. | IT Solution Owner / Business Owner / QA | After actions 001-011 | Open | NL-MES-VSR-001 |

ACTION CONTROL

All 12 actions are Open. Actions are gate-dated rather than assigned fictional calendar dates. G5/G6 and any production/release decision require objective closure evidence, not a status edit in this report.

# 12 IT implementation conclusions

| Q0359350 conclusion area | Evidence / final approved DUMMY version | Reported conclusion | Decision |
| --- | --- | --- | --- |
| Design | FS/IS/DS/CS/DIA/DRR/TRM v0.1; IQR activation evidence | Design baseline supports scoped simulated IQ/recovery progression; final intended-use/operational design conclusion is deferred | Partial / scoped |
| Development and test | CS/IQP/IQTC/DEFL/DEVL/IQR v0.1 | Configured installation evidence is complete in simulation; real supplier/custom-code development verification is not concluded | Partial |
| Installation verification | IQR v0.1 | 32/32 cases and final 224/224 steps Passed after 14 closed exceptions | Successful (simulated) |
| Operational/performance/user verification | No approved OV/PfV/UAT report | Not performed; performance across operating ranges and user requirements is not concluded | Not Met |
| Production installation/performance verification | No approved pIV/pPfV report or production baseline | Not performed; no production installation is represented | Not Met |
| Backup/recovery | BRVR/IRP/IRTR v0.1 | Isolated DUMMY capability/exercise successful; operational process/cadence remains open | Successful - simulation only |
| Risk management | ITRA/ITRRA/DIA/SUPA/TRM and verification evidence | Controls are mapped and partly evidenced; all 26 risks remain Open and residual acceptance is absent | Not Met for release |
| Release for production | No release/change record; G4/G5 Not Met | NOT AUTHORISED | Not released |
| Release for use | No production verification, VSR, training or handover; G5/G6 Not Met | NOT AUTHORISED | Not released |
| Overall | This IREP plus the 22-source baseline | Implementation report is accepted as an accurate DUMMY stage report. The solution is not concluded fit for intended use, validated, ready for production, released for use or handed over. | REPORT APPROVED / RELEASE DEFERRED |

FINAL REPORT CONCLUSION

OVERALL CONCLUSION - IMPLEMENTATION REPORT ACCEPTED; RELEASE DEFERRED. Scoped DUMMY planning, design, IQ and recovery evidence is complete and internally coherent. G4, G5 and G6 are Not Met. No production deployment, release for use, operational handover, residual-risk acceptance, validated-state claim or real Novo Nordisk approval is made or authorised.

# 13 Recommendations and next lifecycle step

| Priority | Recommendation | Required outcome |
| --- | --- | --- |
| 1 | Complete ACT-IREP-001 through -004 | Authoritative product, supplier, environment, interface and security baseline |
| 2 | Complete ACT-IREP-005 through -006 | Full intended-use and production verification plus controlled cutover/rollback evidence |
| 3 | Complete ACT-IREP-007 through -009 | Operational procedures, manuals, SLA, migration decision and training/handover evidence |
| 4 | Complete ACT-IREP-010 through -011 | Control effectiveness, residual-risk acceptance and real controlled repositories/change/release records |
| 5 | Issue NL-MES-VSR-001 and decide G5/G6 | Evidence-backed final recommendation; communicate release only if formally approved |

Per the MLGP, the next document in sequence is NL-MES-OMSOP-001, Operation and Maintenance SOP. Creating that document will address part of DUMMY-DRF-MES-007 and ACT-IREP-007 but will not, by itself, close release or handover readiness.

# 14 References

| Reference | Controlled state | Use in this report |
| --- | --- | --- |
| Q0359350 IT Implementation Plan and Report Template | v2.0; Approved | Reporting activities, deliverables, plan changes and conclusion structure |
| Q187219 Manage IT systems including digital solutions | v12.0; Effective 20 Aug 2025 | Risk-based lifecycle, design, verification, release and operation requirements |
| Q0715589 Acceptance verification and release of IT systems | v1.0; Approved 02 Nov 2021 | Verification reporting, operation readiness and formal release boundary |
| Q0359339 Manage documentation for IT solutions | v4.0; Approved 18 Nov 2024 | Controlled implementation reporting and lifecycle document types |
| Q0359333 Checklist for handover of IT solution | v2.0; Approved 27 Jun 2025 | Handover evidence domains and action-plan need |
| Q218515 Science- and Risk-based Validation | v8.0; Effective 01 Jun 2026 | Critical aspects, risk-based verification and validated-state boundary |
| Q187655 Manage Information Security in IT Solutions | v3.0; Effective 02 Oct 2023 | Security risk/control scope |
| Q204010 Manage data integrity in IT solutions | v8.0; supplied Issued/Training Copy; Verify | Data-integrity lifecycle and applicability boundary |
| Q216301 Manage IT infrastructure | v7.0; supplied issued/proposed state; Verify | Infrastructure planning/qualification context |
| NL-MES-IPLAN-001 | v0.1; simulated approved | Approved plan reported by this document |
| NL-MES-MLGP-001 / SYS-001 | v0.1; simulated approved | Lifecycle sequence and system boundary |
| NL-MES-URS-001 / ITRA-001 / ITRRA-001 / SUPA-001 | v0.1; simulated approved | Requirement, risk and supplier baselines |
| NL-MES-FS-001 / IS-001 / DS-001 / CS-001 / DIA-001 / DRR-001 / TRM-001 | v0.1; simulated approved | Design, data and traceability evidence |
| NL-MES-IQP-001 / IQTC-001 / DEFL-001 / DEVL-001 / IQR-001 | v0.1; simulated approved | IQ plan, execution, exceptions and conclusion |
| NL-MES-BRVR-001 / IRP-001 / IRTR-001 | v0.1; simulated approved | Backup/restore and recovery evidence |

# 15 Change log

| Version | Date | Controlled change | Impact / disposition |
| --- | --- | --- | --- |
| 0.1 | 11 Aug 2026 | Initial IT Implementation Report | Reports NL-MES-IPLAN-001 actual DUMMY state; no source plan or source document modified |

# Appendix A - Final deliverable register

| Seq | Code | Document ID | Deliverable | Approved version | Reported state | Evidence | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | MLGP | NL-MES-MLGP-001 | Master Lifecycle Generation Plan | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-MLGP-Master Lifecycle Generation Plan-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 2 | SYS | NL-MES-SYS-001 | System Overview and Description | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-SYS-System Overview and Description-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 3 | IPLAN | NL-MES-IPLAN-001 | IT Implementation Plan | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-IPLAN-IT Implementation Plan-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 4 | URS | NL-MES-URS-001 | User Requirement Specification | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-URS-User Requirement Specification-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 5 | ITRA | NL-MES-ITRA-001 | IT Risk Assessment | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-ITRA-IT Risk Assessment-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 6 | ITRRA | NL-MES-ITRRA-001 | IT Requirement Risk Assessment | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-ITRRA-IT Requirement Risk Assessment-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 7 | SUPA | NL-MES-SUPA-001 | Supplier Assessment Report | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-SUPA-Supplier Assessment Report-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 8 | FS | NL-MES-FS-001 | Functional Specification | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-FS-Functional Specification-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 9 | IS | NL-MES-IS-001 | Integration Specification | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-IS-Integration Specification-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 10 | DS | NL-MES-DS-001 | Design Specification | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-DS-Design Specification-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 11 | CS | NL-MES-CS-001 | Configuration Specification | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-CS-Configuration Specification-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 12 | DIA | NL-MES-DIA-001 | Data Integrity Assessment | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-DIA-Data Integrity Assessment-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 13 | DRR | NL-MES-DRR-001 | Design Review Report | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-DRR-Design Review Report-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 14 | TRM | NL-MES-TRM-001 | Traceability Matrix | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-TRM-Traceability Matrix-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 15 | IQP | NL-MES-IQP-001 | Installation Qualification Protocol | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-IQP-Installation Qualification Protocol-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 16 | IQTC | NL-MES-IQTC-001 | IQ Test Cases | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-IQTC-IQ Test Cases-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 17 | DEFL | NL-MES-DEFL-001 | Defect Log | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-DEFL-Defect Log-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 18 | DEVL | NL-MES-DEVL-001 | Deviation Log | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-DEVL-Deviation Log-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 19 | IQR | NL-MES-IQR-001 | IQ Report | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-IQR-IQ Report-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 20 | BRVR | NL-MES-BRVR-001 | Backup and Restore Verification Report | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-BRVR-Backup and Restore Verification Report-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 21 | IRP | NL-MES-IRP-001 | IT Recovery Plan | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-IRP-IT Recovery Plan-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 22 | IRTR | NL-MES-IRTR-001 | IT Recovery Test Protocol and Report | 0.1 | Issued / Final Approved (simulated) | NOVOLIFE-MES-IRTR-IT Recovery Test Protocol and Report-v0.1-DUMMY.docx | Controlled DUMMY source; unchanged by this report |
| 23 | IREP | NL-MES-IREP-001 | IT Implementation Report | 0.1 | Issued / Final Approved (simulated) | This controlled report | Reports actual DUMMY implementation state and unresolved items |
| 24 | OMSOP | NL-MES-OMSOP-001 | Operation and Maintenance SOP | No approved version | Open / not issued | No controlled DOCX in the reporting baseline | Required before final release/handover conclusion |
| 25 | UG | NL-MES-UG-001 | User Guide | No approved version | Open / not issued | No controlled DOCX in the reporting baseline | Required before final release/handover conclusion |
| 26 | AG | NL-MES-AG-001 | Administrator Guide | No approved version | Open / not issued | No controlled DOCX in the reporting baseline | Required before final release/handover conclusion |
| 27 | SLA | NL-MES-SLA-001 | Service Level Agreement | No approved version | Open / not issued | No controlled DOCX in the reporting baseline | Required before final release/handover conclusion |
| 28 | TRN | NL-MES-TRN-001 | Training Package | No approved version | Open / not issued | No controlled DOCX in the reporting baseline | Required before final release/handover conclusion |
| 29 | VSR | NL-MES-VSR-001 | Validation Summary Report | No approved version | Open / not issued | No controlled DOCX in the reporting baseline | Required before final release/handover conclusion |

DELIVERABLE RECONCILIATION

Exactly 23 deliverables are issued including this IREP. Exactly six downstream deliverables remain Open: NL-MES-OMSOP-001, UG-001, AG-001, SLA-001, TRN-001 and VSR-001.

# Appendix B - Implementation activity register

| Activity | Phase | Planned implementation activity | Reported status | Evidence / disposition |
| --- | --- | --- | --- | --- |
| IPA-IREP-001 | P0 | Approve DUMMY lifecycle scope and document sequence | Complete (simulated) | NL-MES-MLGP-001 |
| IPA-IREP-002 | P0 | Establish system boundary and intended-use context | Complete (simulated) | NL-MES-SYS-001 |
| IPA-IREP-003 | P0 | Approve implementation strategy, roles and dependencies | Complete (simulated) | NL-MES-IPLAN-001 |
| IPA-IREP-004 | P0 | Define document/change/defect/deviation routes | Complete (simulated) | IPLAN / DEFL / DEVL |
| IPA-IREP-005 | P0 | Record G0 planning baseline | Complete (simulated) | IPLAN / MLGP |
| IPA-IREP-006 | P1 | Approve 50-requirement URS baseline | Complete (simulated) | NL-MES-URS-001 |
| IPA-IREP-007 | P1 | Complete gross-risk and lifecycle-control assessment | Complete - baseline only | NL-MES-ITRA-001; 26 risks Open |
| IPA-IREP-008 | P1 | Complete requirement-level risk assessment | Complete - baseline only | NL-MES-ITRRA-001 |
| IPA-IREP-009 | P1 | Assess supplier and service dependence | Complete - conditional | NL-MES-SUPA-001; GxP delivery blocked |
| IPA-IREP-010 | P1 | Record G1 requirements/risk baseline | Complete (simulated) | URS / ITRA / ITRRA / SUPA |
| IPA-IREP-011 | P2 | Approve functional design for all 50 requirements | Complete (simulated) | NL-MES-FS-001 |
| IPA-IREP-012 | P2 | Approve 60 integration requirements and design controls | Complete (simulated) | NL-MES-IS-001 |
| IPA-IREP-013 | P2 | Approve technical and configuration design baselines | Complete (simulated) | NL-MES-DS-001 / CS-001 |
| IPA-IREP-014 | P2 | Complete data-integrity assessment and final design review | Complete - conditional | NL-MES-DIA-001 / DRR-001 |
| IPA-IREP-015 | P2 | Establish bidirectional trace baseline | Complete - planning baseline | NL-MES-TRM-001 |
| IPA-IREP-016 | P3 | Establish controlled DUMMY configuration/installation baseline | Complete (simulated) | CS / IQP / IQTC / IQR |
| IPA-IREP-017 | P3 | Obtain real supplier development, product and custom-object evidence | Open | SUPA conditions; VER-IPLAN-001/007/008 |
| IPA-IREP-018 | P3 | Approve IQ protocol and 32 test cases | Complete (simulated) | NL-MES-IQP-001 / IQTC-001 |
| IPA-IREP-019 | P3 | Operate defect and validation-deviation controls | Complete (simulated) | 8 defects + 6 deviations closed |
| IPA-IREP-020 | P3 | Close IQ activation findings and readiness gates | Complete - scoped | 9 gate findings closed; DUMMY-DRF-MES-007 open/non-gate |
| IPA-IREP-021 | P4 | Execute and report installation qualification | Complete (simulated) | 32/32 cases; 224/224 final accepted steps Passed |
| IPA-IREP-022 | P4 | Verify backup and restore capability | Complete (simulated) | NL-MES-BRVR-001; 12/12 activities Passed |
| IPA-IREP-023 | P4 | Approve recovery plan and execute recovery exercise | Complete (simulated) | IRP / IRTR; all objectives and criteria Met |
| IPA-IREP-024 | P4 | Execute OV/PfV/UAT or equivalent intended-use verification | Not performed / Open | No approved report in baseline |
| IPA-IREP-025 | P4 | Execute production IV/PfV and final production baseline | Not performed / Open | No production activity represented |
| IPA-IREP-026 | P5 | Perform simulated deployment/handover readiness review | Complete - assessment only | IREP phase/gate and action registers |
| IPA-IREP-027 | P5 | Deploy to production and approve cutover/rollback evidence | Not performed | No production deployment |
| IPA-IREP-028 | P5 | Approve O&M SOP, user/admin guides and SLA | Open | NL-MES-OMSOP/UG/AG/SLA not issued |
| IPA-IREP-029 | P5 | Complete role-based operational and end-user training | Open | NL-MES-TRN-001 not issued |
| IPA-IREP-030 | P5 | Complete ownership, support and knowledge-transfer handover | Open | G6 prerequisites incomplete |
| IPA-IREP-031 | P6 | Issue implementation report | Complete (simulated) | NL-MES-IREP-001 |
| IPA-IREP-032 | P6 | Report plan variances and unresolved items | Complete (simulated) | IREP Sections 10-11 |
| IPA-IREP-033 | P6 | Rate and accept residual risks | Open | 26 risks Open; 0 accepted |
| IPA-IREP-034 | P6 | Issue VSR and final release recommendation | Deferred | NL-MES-VSR-001 not issued |
| IPA-IREP-035 | P6 | Approve G5 release readiness and G6 handover | Not Met | Release/handover prohibited by this report |

# Appendix C - Plan Verify-item disposition

| Verify item | Question / uncertainty | IREP disposition | Evidence basis | Required action |
| --- | --- | --- | --- | --- |
| VER-IPLAN-001 | Exact PAS-X release/modules/supplier product and service model | Open | SUPA condition; no real product/supplier evidence | ACT-IREP-001/002 |
| VER-IPLAN-002 | Hosting/sites/zones/topology/data residency | Partially addressed | SYS/DS conceptual design; authoritative deployment values remain Verify | ACT-IREP-003 |
| VER-IPLAN-003 | Environment names/segregation/baselines/promotion/PROD comparability | Partially addressed | DUMMY TEST/VAL baseline evidenced; no production comparison | ACT-IREP-003/006 |
| VER-IPLAN-004 | Integration products, owners and versions | Partially addressed | IS ownership/design baseline; actual products/versions remain Verify | ACT-IREP-001/004 |
| VER-IPLAN-005 | Interface protocols/endpoints/payloads/mappings/security/retry values | Partially addressed | 60 design requirements; live values and end-to-end evidence absent | ACT-IREP-004 |
| VER-IPLAN-006 | Risk method, scoring, thresholds and acceptance | Partially addressed | Working method established; residual rating and acceptance absent | ACT-IREP-009 |
| VER-IPLAN-007 | Software categories and custom-code inventory | Partially addressed | Category 4 working basis; custom-object decision not authoritative | ACT-IREP-001 |
| VER-IPLAN-008 | Supplier QMS, evidence, service allocation and agreements | Open | Supplier conditionally fit for planning only | ACT-IREP-002 |
| VER-IPLAN-009 | Data authority, criticality, retention and migration | Partially addressed | DIA issued; authoritative retention/migration applicability open | ACT-IREP-008 |
| VER-IPLAN-010 | Security/access/roles/SoD/SSO/MFA/service accounts/certificates/privacy | Partially addressed | Design and IQ controls evidenced; operating values/processes open | ACT-IREP-004/007/011 |
| VER-IPLAN-011 | Signature meaning and audit-trail requirements | Partially addressed | URS/design/IQ trace present; intended-use verification open | ACT-IREP-005 |
| VER-IPLAN-012 | Performance, capacity, availability and workload | Open | No approved performance/capacity result | ACT-IREP-005/007 |
| VER-IPLAN-013 | RTO/RPO/backup/recovery | Closed for DUMMY / Verify operational | BRVR/IRP/IRTR passed in isolated simulation | Operational approval/cadence in ACT-IREP-007 |
| VER-IPLAN-014 | Deployment window, cutover, rollback, pre-backup and reconciliation | Open | No production cutover package or execution | ACT-IREP-006 |
| VER-IPLAN-015 | Repositories, workflows, approvals, retention and access | Open | Simulation folder only; real controlled systems not represented | ACT-IREP-010 |
| VER-IPLAN-016 | Operational procedures, support, SLA, monitoring, incident/change and handover | Open | Six downstream operational/release deliverables absent | ACT-IREP-007/011 |
| VER-IPLAN-017 | Controlled applicability of Q216301 and Q204010 | Open / Verify | Supplied copies retain applicability/status verification need | ACT-IREP-010 |
| VER-IPLAN-018 | Need for additional separate records | Partially addressed | Current MLGP split accepted; migration/security/operational records remain scope dependent | ACT-IREP-008/011 |

# Appendix D - Assumption disposition

| Assumption | IPLAN basis | IREP disposition | Follow-up |
| --- | --- | --- | --- |
| ASM-IPLAN-001 | All content is fictional and for training/hackathon use. | Confirmed for this report | Retain DUMMY warnings and simulated approvals |
| ASM-IPLAN-002 | Novo Life MES PAS-X is a new GxP-critical implementation. | Retained assumption | Verify authoritative system/business criticality before real use |
| ASM-IPLAN-003 | Implementation plan and report are separate controlled records. | Confirmed | NL-MES-IPLAN-001 remains unchanged; this IREP reports outcomes |
| ASM-IPLAN-004 | Configured software category 4; no custom code assumed. | Partially confirmed | Working design basis only; custom-object inventory remains open |
| ASM-IPLAN-005 | No legacy migration; initial configuration/data load only. | Retained / Verify | Migration applicability remains an open action |
| ASM-IPLAN-006 | DEV/TEST/VAL/PROD/DR are segregated. | Confirmed for conceptual DUMMY model | Actual environments and production comparability remain Verify |
| ASM-IPLAN-007 | Supplier evidence becomes usable only after assessment. | Confirmed | Supplier evidence/agreements are still open; no reliance for release |
| ASM-IPLAN-008 | W01-W32 schedule is illustrative. | Confirmed | Reported dates are DUMMY record dates, not a real project schedule |

# Appendix E - Gate and open-action register

| Gate | Decision | Reported result | Evidence basis | Permitted progression / boundary |
| --- | --- | --- | --- | --- |
| G0 | Plan baseline | Met (simulated) | MLGP, SYS and IPLAN approved | Progress to requirements/risk baseline only |
| G1 | Requirements and risk baseline | Met (simulated) | 50 URS; ITRA/ITRRA/SUPA issued | Risk treatment/effectiveness/residual acceptance remain later activities |
| G2 | Design readiness | Scoped Met | FS/IS/DS/CS/DIA/DRR/TRM; 9 gate findings closed before IQ | Supports DUMMY IQ progression; not final production/readiness conclusion |
| G3 | Verification readiness | Scoped Met | IQ/recovery plans, cases, baselines and exception controls activated | Applies only to executed IQ/BRVR/IRTR scope |
| G4 | Deployment readiness | Not Met | OV/PfV/UAT, production verification and cutover evidence absent | Do not deploy to production |
| G5 | Release readiness | Not Met | 26 risks Open; VSR and operational package absent | Do not release for production or use |
| G6 | Handover | Not Met | OMSOP/UG/AG/SLA/TRN and ownership transfer absent | Do not hand over to operations |

| Action | Required closure | Owner role | Due gate | Status | Trace |
| --- | --- | --- | --- | --- | --- |
| ACT-IREP-001 | Confirm exact PAS-X release, modules, product, custom-object inventory and supported deployment model. | IT Solution Owner / Supplier Representative | Before G4 | Open | VER-IPLAN-001/007; SUPA |
| ACT-IREP-002 | Complete supplier qualification, QMS/security evidence, responsibility split, agreements and service commitments. | IT Solution Owner / Supplier Manager | Before G4/G5 | Open | SUPA; VER-IPLAN-008 |
| ACT-IREP-003 | Approve actual environment/topology inventory, production baseline, comparability, capacity and monitoring thresholds. | Infrastructure / Security Lead | Before G4 | Open | VER-IPLAN-002/003/012 |
| ACT-IREP-004 | Approve actual interface contracts and execute end-to-end interface/security verification. | Integration / Security Lead | Before G4/G5 | Open | VER-IPLAN-004/005/010 |
| ACT-IREP-005 | Execute risk-based OV/PfV/UAT or equivalent intended-use verification and report results. | Verification Lead / Business Process Owner | Before G5 | Open | IPA-IREP-024 |
| ACT-IREP-006 | Approve cutover/rollback plan and execute pIV/pPfV plus final production baseline comparison. | Project / IT Solution Manager | Before G5 | Open | VER-IPLAN-014; IPA-IREP-025/027 |
| ACT-IREP-007 | Issue OMSOP, User Guide, Administrator Guide and SLA; close DUMMY-DRF-MES-007. | Operations Lead / IT Solution Owner | Before G5/G6 | Open | NL-MES-OMSOP/UG/AG/SLA; DUMMY-DRF-MES-007 |
| ACT-IREP-008 | Confirm migration/initial-load applicability and approve plan/report if applicable. | Data Owner / Validation Lead | Before G4/G5 | Open | VER-IPLAN-009/018; RSK-MES-026 |
| ACT-IREP-009 | Complete training package, role assignment, qualification evidence and operational knowledge transfer. | Training Coordinator / Operations Lead | Before G5/G6 | Open | NL-MES-TRN-001 |
| ACT-IREP-010 | Implement/evaluate all risk controls, rate residual risks and obtain authorised acceptance with QA involvement. | IT Solution Owner / QA | Before G5 | Open | RSK-MES-001..026 |
| ACT-IREP-011 | Resolve actual document repositories, approvals, release/change record and retention/access controls. | Document Owner / IT Solution Manager | Before G5 | Open | VER-IPLAN-015/017 |
| ACT-IREP-012 | Issue VSR, decide G5/G6, communicate authorised release if approved and complete handover acceptance. | IT Solution Owner / Business Owner / QA | After actions 001-011 | Open | NL-MES-VSR-001 |

# Appendix F - Exception and finding detail

## F1 Design-review findings

| Finding | Topic | IREP status | Evidence / handoff |
| --- | --- | --- | --- |
| DUMMY-DRF-MES-001 | Product/release/modules/software-category evidence | Closed before simulated IQ | IQR activation evidence |
| DUMMY-DRF-MES-002 | Physical architecture/environment/capacity/DR evidence | Closed before simulated IQ | IQR activation evidence |
| DUMMY-DRF-MES-003 | Interface technical contracts and actual values | Closed before simulated IQ | IQR activation evidence |
| DUMMY-DRF-MES-004 | Product-specific configuration objects and values | Closed before simulated IQ | IQR activation evidence |
| DUMMY-DRF-MES-005 | IAM/time/backup/monitoring/recovery service inputs | Closed before simulated IQ | IQR activation evidence |
| DUMMY-DRF-MES-006 | Supplier design-space/lifecycle/security evidence | Closed before simulated IQ | IQR activation evidence |
| DUMMY-DRF-MES-007 | Operational SOP/guides/SLA/review/training handoff | Open - lifecycle follow-up | Future OMSOP/UG/AG/SLA/TRN |
| DUMMY-DRF-MES-008 | Custom code/scripts/reports/adapters applicability | Closed before simulated IQ | IQR activation evidence |
| DUMMY-DRF-MES-009 | Dedicated traceability matrix and test IDs | Closed before simulated IQ | IQR activation evidence |
| DUMMY-DRF-MES-010 | Migration/initial-load applicability decision | Closed before simulated IQ | IQR activation evidence |

## F2 IQ defects

| Defect | Class | Origin | Status | Rerun | IREP implication |
| --- | --- | --- | --- | --- | --- |
| DUMMY-DEF-MES-001 | Major | DUMMY-TC-MES-IQ-005 / step 4 | Closed (simulated) | Passed (simulated) | No residual IQ validity impact (simulated) |
| DUMMY-DEF-MES-002 | Major | DUMMY-TC-MES-IQ-006 / step 4 | Closed (simulated) | Passed (simulated) | No residual IQ validity impact (simulated) |
| DUMMY-DEF-MES-003 | Minor (Non-Obvious) | DUMMY-TC-MES-IQ-010 / step 6 | Closed (simulated) | Passed (simulated) | No residual IQ validity impact (simulated) |
| DUMMY-DEF-MES-004 | Major | DUMMY-TC-MES-IQ-011 / step 3 | Closed (simulated) | Passed (simulated) | No residual IQ validity impact (simulated) |
| DUMMY-DEF-MES-005 | Major | DUMMY-TC-MES-IQ-013 / step 5 | Closed (simulated) | Passed (simulated) | No residual IQ validity impact (simulated) |
| DUMMY-DEF-MES-006 | Minor (Non-Obvious) | DUMMY-TC-MES-IQ-016 / step 6 | Closed (simulated) | Passed (simulated) | No residual IQ validity impact (simulated) |
| DUMMY-DEF-MES-007 | Major | DUMMY-TC-MES-IQ-020 / step 3 | Closed (simulated) | Passed (simulated) | No residual IQ validity impact (simulated) |
| DUMMY-DEF-MES-008 | Major | DUMMY-TC-MES-IQ-027 / step 4 | Closed (simulated) | Passed (simulated) | No residual IQ validity impact (simulated) |

## F3 Validation deviations

| Deviation | Class | Origin | Status | Rerun | IREP implication |
| --- | --- | --- | --- | --- | --- |
| DUMMY-DEV-MES-001 | Major | DUMMY-TC-MES-IQ-002 / step 3 | Closed (simulated) | Passed (simulated) | Validity implication resolved (simulated) |
| DUMMY-DEV-MES-002 | Major | DUMMY-TC-MES-IQ-022 / step 4 | Closed (simulated) | Passed (simulated) | Validity implication resolved (simulated) |
| DUMMY-DEV-MES-003 | Minor (Non-Obvious) | DUMMY-TC-MES-IQ-028 / step 3 | Closed (simulated) | Passed (simulated) | Validity implication resolved (simulated) |
| DUMMY-DEV-MES-004 | Minor (Non-Obvious) | DUMMY-TC-MES-IQ-029 / step 6 | Closed (simulated) | Passed (simulated) | Validity implication resolved (simulated) |
| DUMMY-DEV-MES-005 | Minor (Obvious) | DUMMY-TC-MES-IQ-025 / step 6 | Closed (simulated) | Passed (simulated) | Validity implication resolved (simulated) |
| DUMMY-DEV-MES-006 | Minor (Obvious) | DUMMY-TC-MES-IQ-030 / step 6 | Closed (simulated) | Passed (simulated) | Validity implication resolved (simulated) |

# Appendix G - Risk status register

| Risk | Scenario | Working level | Implementation evidence state | Status | Residual / acceptance |
| --- | --- | --- | --- | --- | --- |
| RSK-MES-001 | Unapproved order, recipe, or execution state | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-002 | Incorrect or incomplete execution data and calculations | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-003 | Incomplete batch completion, exception disposition, or review | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-004 | Loss, unreadability, or incomplete copy of regulated records | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-005 | Unauthorised or excessive access | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-006 | Credential, session, or service-account compromise | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-007 | Invalid or non-attributable electronic signature | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-008 | Incomplete, alterable, or ineffective audit trail | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-009 | Inconsistent time and chronology | Working Medium | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-010 | Uncontrolled correction, deletion, or record lifecycle | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-011 | ERP order/master-data or confirmation interface failure | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-012 | LIMS sample, result, or disposition interface failure | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-013 | Automation command, state, or measurement mismatch | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-014 | Historian/reporting publication incomplete or misleading | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-015 | Cross-interface integrity, monitoring, or reconciliation failure | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-016 | Application/infrastructure unavailability or capacity exhaustion | Working High | Design, IQ and recovery evidence available; operational/supplier controls incomplete | Open | Not rated / not accepted |
| RSK-MES-017 | Backup incomplete, corrupt, unavailable, or outside need | Working High | Design, IQ and recovery evidence available; operational/supplier controls incomplete | Open | Not rated / not accepted |
| RSK-MES-018 | Recovery misses objectives or creates inconsistent state | Working High | Design, IQ and recovery evidence available; operational/supplier controls incomplete | Open | Not rated / not accepted |
| RSK-MES-019 | Cyber vulnerability, malware, or insecure component | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-020 | Supplier or shared-service controls unclear or ineffective | Working High | Design, IQ and recovery evidence available; operational/supplier controls incomplete | Open | Not rated / not accepted |
| RSK-MES-021 | Uncontrolled change, configuration, or promotion | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-022 | Incident/problem handling fails to protect GxP state | Working High | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-023 | Controlled report or extract misinterpreted or altered | Working Medium | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-024 | Maintained-state controls, review, or training ineffective | Working Medium | Design, IQ and recovery evidence available; operational/supplier controls incomplete | Open | Not rated / not accepted |
| RSK-MES-025 | Personal-data processing excessive or insufficiently protected | Working Medium | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |
| RSK-MES-026 | Initial load or migration loses content and meaning | Working High if applicable | Design/IQ/recovery evidence available; full lifecycle effectiveness incomplete | Open | Not rated / not accepted |

RISK RECONCILIATION

All 26 risks are Open. Successful DUMMY IQ or recovery evidence does not create a residual rating or authorised acceptance. Risk control effectiveness and acceptance remain ACT-IREP-010.

# Appendix H - Controlled source-document baseline

| Code | Controlled DUMMY source | SHA-256 | Bytes |
| --- | --- | --- | --- |
| BRVR | NOVOLIFE-MES-BRVR-Backup and Restore Verification Report-v0.1-DUMMY.docx | EA7C6009C110DD5F4C8C01C393FD654DE1527C3AB5AA7727AE2F86F87B795DE9 | 64804 |
| CS | NOVOLIFE-MES-CS-Configuration Specification-v0.1-DUMMY.docx | 8F4078E36FED3D3A523A0A4BB565E9BBCCF1DFF32112E53BCA6EE4ECE1EA97FC | 91307 |
| DEFL | NOVOLIFE-MES-DEFL-Defect Log-v0.1-DUMMY.docx | BDB8CF30C89EF0904F5CBA509AE908318F03C7D70EE70A8F9B90898AD3743E75 | 79930 |
| DEVL | NOVOLIFE-MES-DEVL-Deviation Log-v0.1-DUMMY.docx | 7D03DCD025F3838D49E612C5D75F2980AFF066579E84C530CE6B984036FE5DCF | 74298 |
| DIA | NOVOLIFE-MES-DIA-Data Integrity Assessment-v0.1-DUMMY.docx | B796EC45FE517BA95C9722CE28D96B6D791586CFDEFD489E2714F7D093102DC8 | 94744 |
| DRR | NOVOLIFE-MES-DRR-Design Review Report-v0.1-DUMMY.docx | B813A6952F062902386D0167B1EC80D035B4480B878978B82796319A515D0B4C | 75977 |
| DS | NOVOLIFE-MES-DS-Design Specification-v0.1-DUMMY.docx | E1A8E41194D607D8ADB8B042B8D2AD29A587D7FC24E26D34A20AB19560B79392 | 90588 |
| FS | NOVOLIFE-MES-FS-Functional Specification-v0.1-DUMMY.docx | 8E40D5921E7A77A8BF15C263D5F7DB692DC4CD397339D2BB14B6F647872B9618 | 77007 |
| IPLAN | NOVOLIFE-MES-IPLAN-IT Implementation Plan-v0.1-DUMMY.docx | B285EC5379FB80AE89CE087756E096B4D678A029BCDCF7521F8C07C2465AB1C9 | 65078 |
| IQP | NOVOLIFE-MES-IQP-Installation Qualification Protocol-v0.1-DUMMY.docx | 41EB6086AA6F424BFEEDE6AEFD5872049AB84281A16B5329D97AD8E5CF9ECA68 | 79587 |
| IQR | NOVOLIFE-MES-IQR-IQ Report-v0.1-DUMMY.docx | 4B329CEC3B474FC3F35DBD60CDFD4FCC6654502CFB3894A1BD59261F3A2BDA67 | 68428 |
| IQTC | NOVOLIFE-MES-IQTC-IQ Test Cases-v0.1-DUMMY.docx | FB142153117CF0CC9A684951363E74D74D82B09C525ABF8045E16309163B6029 | 182285 |
| IRP | NOVOLIFE-MES-IRP-IT Recovery Plan-v0.1-DUMMY.docx | D1214D7E47B8BEBB13AC8417D8E7C6E8D78DDA345B6E9232767ED2BFF28D91C6 | 79870 |
| IRTR | NOVOLIFE-MES-IRTR-IT Recovery Test Protocol and Report-v0.1-DUMMY.docx | E33969B33885D400CEBD5EA28486E0E8738BF5C897BA68B9FD6FB84CC4696E79 | 81110 |
| IS | NOVOLIFE-MES-IS-Integration Specification-v0.1-DUMMY.docx | E7E96103779203A8E8652B119C04C0F7D6860F05E3173173029DD880C81DE32F | 90712 |
| ITRA | NOVOLIFE-MES-ITRA-IT Risk Assessment-v0.1-DUMMY.docx | 6D91B4D8B1EB9771FC767987AC42AB1E68E548B880F9071EE9522837285B5798 | 82700 |
| ITRRA | NOVOLIFE-MES-ITRRA-IT Requirement Risk Assessment-v0.1-DUMMY.docx | A63BC70EB0BA184AF0544DE78C18DBFBCE00585F3BD2B25FAA6AF478BB42BEAF | 89244 |
| MLGP | NOVOLIFE-MES-MLGP-Master Lifecycle Generation Plan-v0.1-DUMMY.docx | 58DF06F0CFDD20FDAE47DB054D62B66DA640576CDCD2B14132502E6C60277453 | 64240 |
| SUPA | NOVOLIFE-MES-SUPA-Supplier Assessment Report-v0.1-DUMMY.docx | DF2BD6401E9105CE5DC9EC28E9D2D60F3776E2B7A3852D06D6368B12AE2C8BDA | 67356 |
| SYS | NOVOLIFE-MES-SYS-System Overview and Description-v0.1-DUMMY.docx | 0C2D6C7F6CA960538A78DD91DB130ECA9384B1A251458700B2AABEB71B94E987 | 60205 |
| TRM | NOVOLIFE-MES-TRM-Traceability Matrix-v0.1-DUMMY.docx | 9081D1DB2E675AE7EA2F86FA31B4717EFD4A664674BC4DA5992A6CCB79DDAFBC | 85691 |
| URS | NOVOLIFE-MES-URS-User Requirement Specification-v0.1-DUMMY.docx | FC480E613AF60A29C59B293EC7F0F42D14C1ECA3B1C8D7A3E63C372D78C6B856 | 88124 |

SOURCE PRESERVATION

All 22 source DOCX files were reconciled and were not modified by creation of NL-MES-IREP-001. This report adds one new controlled Word file to the target folder.

# Appendix I - Quality gate register

| Quality gate | Check | Result | Evidence |
| --- | --- | --- | --- |
| IREP-QG-01 | MLGP sequence 23 and 22-source baseline | Pass | Reconciliation / Appendix H |
| IREP-QG-02 | Q0359350 report sections and final deliverable versions | Pass | Sections 5-15 / Appendix A |
| IREP-QG-03 | 35 planned activities reported without plan rewrite | Pass | Section 5 / Appendix B |
| IREP-QG-04 | 10 plan variances explicitly dispositioned | Pass | Section 10 |
| IREP-QG-05 | 18 Verify items and 8 assumptions dispositioned | Pass | Appendices C-D |
| IREP-QG-06 | G0-G6 evidence decisions; G4-G6 Not Met | Pass | Section 5.3 / Appendix E |
| IREP-QG-07 | 8 defects + 6 deviations closed; 9 findings closed / 1 open | Pass | Section 7.3 / Appendix F |
| IREP-QG-08 | IQ and recovery exact result populations | Pass | Section 7.1 |
| IREP-QG-09 | 26 risks Open; 0 residual ratings/acceptances | Pass | Sections 6/12 / Appendix G |
| IREP-QG-10 | 23/29 deliverables; six downstream Open | Pass | Section 8 / Appendix A |
| IREP-QG-11 | No production deployment, release, intended-use, validated-state or handover claim | Pass | Final conclusion and content audit |
| IREP-QG-12 | No real identity/contact/link/secret/endpoint or template placeholder | Pass | Privacy/content audit |
| IREP-QG-13 | No comments, tracked changes, custom XML or external relationships | Pass | OOXML audit |
| IREP-QG-14 | Accessibility, exact geometry, all-page render and delivery equality | Pass | Final QA records |

FINAL QA NOTE

Simulated Reviewed and Approved for Demo/Training Use Only. Successful artifact QA does not alter the release-deferred conclusion.