NOVO LIFE

MES PAS-X

Final Validation Summary Report / Release Recommendation

DOCUMENT CLASSIFICATION

DUMMY VALIDATION SUMMARY - evidence-based release decision for a fictional audit/training package. The document is simulated approved; the system release recommendation is HOLD / DEFER.

| Control field | Value |
| --- | --- |
| Document ID | NL-MES-VSR-001 |
| Version | 0.1 |
| Document date | 12 Aug 2026 |
| Document status | Simulated Reviewed and Approved for Demo/Training Use Only. |
| Operating state | PRE-OPERATIONAL / NOT ACTIVATED |
| Release recommendation | HOLD / DEFER - DO NOT RELEASE |
| Package position | Sequence 29 of 35; sequences 30-35 remain planned after VSR |
| System | Fictional Novo Life MES PAS-X |
| Document owner | Fictional Validation Lead / System Owner role |
| Scope | Summary of the frozen 28-file input baseline, release gates, blockers, actions and trace populations |
| Use limitation | Not valid for operational, regulatory, inspection or GxP release use |

APPROVAL VERSUS RELEASE

The words 'reviewed and approved' apply only to this DUMMY document's completeness for simulation. They do not mean that the fictional MES is validated, qualified, deployed, released, handed over or approved for use.

# Simulated review and approval

Role-based approval below records a fictional review of the VSR structure, evidence summary and conservative decision. No real identity, signature, Quality release authority or regulated approval is represented.

| Fictional role | Review focus | Simulated disposition | Release authority created |
| --- | --- | --- | --- |
| Validation Lead | Plan/report alignment, evidence populations and conclusion | Simulated approved | None |
| System Owner | Intended use, lifecycle evidence and action ownership | Simulated approved | None |
| Process Owner | Business/process readiness and handover boundary | Simulated approved | None |
| Quality | Critical aspects, risks, deviations, validation conclusion and release boundary | Simulated approved with HOLD recommendation | None |

## Change history

| Version | Date | Authoring role | Change | Status |
| --- | --- | --- | --- | --- |
| 0.1 | 12 Aug 2026 | Fictional Validation Documentation Author | Initial DUMMY VSR: 28-file evidence baseline, 7 gates, 6 decisions, 12 evidence domains, 12 blockers/actions and full trace reconciliation. | Simulated Reviewed and Approved for Demo/Training Use Only. |

# Executive release decision

| Decision factor | Evidence evaluated | Conclusion | Release effect |
| --- | --- | --- | --- |
| Package integrity | 28 issued Word files hash-reconciled; source populations consistent | Coherent for DUMMY audit/training use | No operational effect |
| Requirements/traceability | 50 URS and 50 FS/DS/CI chains | Scoped Met | Does not prove implemented effectiveness |
| Risk | 26 shared risks | All Open; no residual rating/acceptance | Release blocked |
| Verification | 32/32 IQ cases; 224/224 final accepted steps; 12/12 backup checks - simulated | Synthetic evidence only | Production qualification absent |
| Recovery | 12/12 runs; 40/40 steps; 20/20 checks; 10/10 criteria - simulated | Proposed objectives met in DUMMY context | Production rehearsal/resume authority absent |
| Implementation | IREP, DUMMY-DRF-MES-007 and ACT-IREP-007 | Production implementation/actions Open | Release blocked |
| Operational readiness | OMSOP, UG, AG, SLA and TRN | Design artifacts issued; real activation/qualification absent | Release blocked |
| Quality/handover | G4/G5/G6 | Not Met | No QA release or handover |

FINAL RELEASE DECISION

RELEASE RECOMMENDATION: HOLD / DEFER - DO NOT RELEASE. The validated state is not established. Do not deploy, activate, hand over, grant real access, communicate Release for Use, accept residual risk or use this package for a real GxP decision.

Positive simulated test results are retained as internally consistent DUMMY evidence. They are not rejected; their applicability is bounded. They cannot substitute for verification in the intended production context, effective controls, accountable risk acceptance or Quality release.

# Contents

| Section | Content |
| --- | --- |
| 1 | Purpose, scope and report method |
| 2 | Governing source criteria |
| 3 | System and lifecycle context |
| 4 | Gate assessment |
| 5 | Evidence-domain assessment |
| 6 | Verification and recovery summary |
| 7 | Risk, defect, deviation and action conclusion |
| 8 | Operational readiness and handover |
| 9 | Release decision statements |
| 10 | Release blockers |
| 11 | Closure action plan |
| 12 | Re-evaluation and approval conditions |
| Appendix A | 35-deliverable lifecycle-plan status |
| Appendix B | 28-document immutable input baseline |
| Appendix C | 50-URS release trace |
| Appendix D | 26-risk release trace |
| Appendix E | Source/guidance register and quality gate |

# 1 Purpose, scope and report method

This VSR summarizes the controlled DUMMY lifecycle evidence for fictional Novo Life MES PAS-X, compares it with governing release criteria, states whether the validated state is established, and gives a release recommendation. It does not recreate source evidence or promote simulated observations into production facts.

## 1.1 In scope

The frozen 28-file input baseline; 50 requirements; 26 risks; simulated design, IQ, backup/restore and recovery evidence; implementation reporting; operational/support/training design; lifecycle gates; release blockers; closure actions; and planned maintained-state samples.

## 1.2 Explicit exclusions

Real system execution, real people/signatures, production identifiers/endpoints/credentials, production installation or deployment, batch/product evidence, actual supplier acceptance, real training/access records, live audit trails, Quality release, residual-risk acceptance and handover are excluded.

## 1.3 Assessment method

| Step | Method | Output |
| --- | --- | --- |
| Freeze | Hash and byte-size reconcile every issued root Word file | Immutable 28-document baseline |
| Population | Reconcile 50 URS/FS/DS/CI chains and 26 shared risks | Complete trace populations |
| Criteria | Apply acceptance/release, validation, deviation, documentation and handover guidance | Decision rules |
| Evaluate | Distinguish document issuance from evidence sufficiency and DUMMY evidence from production evidence | Gate/evidence findings |
| Decide | Use the most conservative applicable disposition where a release prerequisite is absent | HOLD / DEFER recommendation |
| Control | Record blockers, owners, required evidence and re-evaluation conditions | Open action plan |

# 2 Governing source criteria

| Source | Status/version | VSR criterion applied |
| --- | --- | --- |
| Acceptance verification and release of IT systems | Q0715589 v1.0 Approved 02 Nov 2021 | Conclude verification outcome; complete and accept planned lifecycle/implementation activities; establish operations/roles; GxP release by QA; local training/procedures ready |
| Science- and Risk-based Validation | Q218515 v8.0 Effective 01 Jun 2026 | Demonstrate fit for intended use and risks mitigated to acceptable level; report plan completion/major changes; conclude validated state; Quality grants final release |
| Validation Deviations | Q0300381 v5.0 Effective 15 Oct 2024 | Assess, classify, correct and disposition discrepancies; critical-aspect/acceptance failures may be major |
| Checklist for handover of IT solution | Q0359333 v2.0 Approved 27 Jun 2025 | Transfer documentation, ownership, knowledge/training and agreed actions for missing evidence |
| Manage IT systems including digital solutions | Q187219 v12.0 | Lifecycle accountability, controlled verification, fit for intended use and release boundary |
| Manage documentation for IT solutions | Q0359339 v4.0 | Controlled, proportionate lifecycle documentation and reference discipline |
| IT Implementation Plan and Report Template | Q0359350 v2.0 | Report planned activities, major changes, results, open actions and fit-for-use conclusion |

DECISION PRINCIPLE

A release report must follow evidence. A simulated approved artifact cannot convert missing production evidence, open risks or unmet gates into an acceptable release condition.

# 3 System and lifecycle context

| Context field | Controlled statement |
| --- | --- |
| System | Fictional Novo Life MES PAS-X supporting a hypothetical regulated manufacturing process |
| Current state | PRE-OPERATIONAL / NOT ACTIVATED |
| Evidence environment | Isolated DUMMY simulation; no live endpoint, production data, real user or operational record |
| Lifecycle plan | 35 documents; 28 inputs issued before this VSR; VSR is sequence 29; six maintained-state samples remain |
| Verification boundary | Positive simulated IQ/backup/recovery results demonstrate document logic only |
| Risk boundary | All 26 shared risks remain Open with no residual rating or acceptance |
| Implementation boundary | No production deployment, production verification, Release for Use or handover |
| Supplier boundary | Supplier Alpha conditional for planning only |

# 4 Gate assessment

| Gate | Decision point | State | Evidence | Implication |
| --- | --- | --- | --- | --- |
| G0 | Authorisation and DUMMY boundary | Met | MLGP and 28-file controlled baseline; exact DUMMY limitation retained | Permits documentation simulation only |
| G1 | Planning and lifecycle scope | Met | MLGP/IPLAN define lifecycle deliverables, roles, dependencies and gates | Does not authorise execution or use |
| G2 | Requirements and risk scope | Scoped Met | 50 URS and 26 shared risks identified and traced | All risks remain Open; no residual acceptance |
| G3 | Design and verification planning | Scoped Met | FS/IS/DS/CS/DIA/DRR/TRM and IQ planning are coherent for DUMMY scope | No production baseline or effectiveness conclusion |
| G4 | Verification and implementation evidence | Not Met | Simulated IQ/recovery evidence exists; production verification/deployment and two cross-package actions remain Open | Blocks release |
| G5 | Operational readiness | Not Met | Procedures, guides, SLA and synthetic training artifacts exist | Real training/access, support activation, supplier readiness and site-specific controls remain Open |
| G6 | Quality release and handover | Not Met | No QA release, validated-state conclusion, residual-risk acceptance or accountable handover | Blocks release and operational use |

GATE CONCLUSION

G0 and G1 are Met; G2 and G3 are Scoped Met; G4, G5 and G6 are Not Met. No rule permits early release while G4-G6 remain Not Met.

# 5 Evidence-domain assessment

| Evidence ID | Domain | Primary documents | Observed state | VSR evaluation |
| --- | --- | --- | --- | --- |
| EVID-VSR-001 | Lifecycle planning | MLGP; IPLAN | Defined and simulated approved | Adequate for DUMMY package control; not an execution authorisation |
| EVID-VSR-002 | System/intended-use definition | SYS; URS | 50 requirements defined | DUMMY scope coherent; intended production context not verified |
| EVID-VSR-003 | Risk management | ITRA; ITRRA; DIA | 26/26 risks Open | Not acceptable for release; no residual risk or acceptance |
| EVID-VSR-004 | Supplier assurance | SUPA; SLA | Supplier Alpha conditional for planning only | Final capability, contract and service acceptance Open |
| EVID-VSR-005 | Design and configuration | FS; IS; DS; CS; DRR | DUMMY design package reviewed | No production as-built/configuration baseline |
| EVID-VSR-006 | Traceability | TRM | 50/50 URS-FS-DS-CI chains mapped | Trace presence does not prove operational effectiveness |
| EVID-VSR-007 | Installation verification | IQP; IQTC; IQR; DEFL; DEVL | 32/32 cases and 224/224 final accepted steps passed in simulation | No production installation baseline; simulated closures only |
| EVID-VSR-008 | Backup and recovery | BRVR; IRP; IRTR | 12/12 backup/restore checks and 12/12 recovery runs passed in simulation | No production rehearsal or regulated-resume authorisation |
| EVID-VSR-009 | Implementation | IREP | DUMMY reporting artifact issued; ACT-IREP-007 Open | No production deployment, verification, change closure or release |
| EVID-VSR-010 | Operation, support and use | OMSOP; UG; AG; SLA | Control designs documented; SLA proposed/not effective | Site-specific runbooks, activation and operating evidence Open |
| EVID-VSR-011 | Training and access readiness | TRN; UG; AG | 11 curricula, 22 synthetic records; 12 activation actions Open | No real learner qualified and no access authorised |
| EVID-VSR-012 | Quality release and handover | VSR; IREP; MLGP | G4/G5/G6 Not Met | No QA release, validated state, handover or use |

Every evidence domain remains traceable to issued source documents. The VSR does not overwrite source results; it evaluates whether the results support the specific release decision.

# 6 Verification and recovery summary

## 6.1 Simulated qualification evidence

| Population | Planned | Reported result | Evidence boundary | Release conclusion |
| --- | --- | --- | --- | --- |
| IQ cases | 32 | 32/32 passed - simulated | Isolated DUMMY execution objects | No production qualification |
| IQ final accepted steps | 224 | 224/224 passed - simulated | Final accepted run state; source protocol remains controlled | No production baseline |
| Backup/restore checks | 12 | 12/12 passed - simulated | DUMMY datasets and evidence locators | No live backup/restore effectiveness |
| Recovery runs | 12 | 12/12 passed - simulated | DUMMY topology, roles and clocks | No production recovery rehearsal |
| Recovery steps/checks/criteria | 40 / 20 / 10 | 40/40; 20/20; 10/10 - simulated | Scenario evidence only | No regulated-resume authority |

## 6.2 Recovery objectives

| Measure | Proposed target | Simulated observation | DUMMY result | Operational conclusion |
| --- | --- | --- | --- | --- |
| RPO | 30 minutes | 18 minutes | Met - simulated | Production objective/evidence not approved |
| RTO | 4 hours | 3 hours 6 minutes | Met - simulated | Production objective/evidence not approved |
| WRT | 2 hours | 1 hour 50 minutes | Met - simulated | Production objective/evidence not approved |
| MTD | 6 hours | 4 hours 56 minutes | Met - simulated | Production objective/evidence not approved |

RECOVERY LIMITATION

The simulated metrics are internally consistent and retained. They do not establish production recovery capability, business acceptance, Quality approval or permission to resume a regulated process.

# 7 Risk, defect, deviation and action conclusion

| Control population | Observed state | VSR conclusion | Release effect |
| --- | --- | --- | --- |
| 26 shared risks | 26 Open; no residual rating or acceptance | Risk mitigation/acceptance criterion not met | Block |
| DUMMY IQ defects | Closed and approved within simulation with passed simulated reruns | Fictional record closure retained | Does not close shared risks or qualify production |
| DUMMY validation deviations | Closed within simulation where applicable | Fictional disposition retained | Does not replace production discrepancy assessment |
| DUMMY-DRF-MES-007 | Open | Cross-package deliverable/readiness follow-up incomplete | Block |
| ACT-IREP-007 | Open | Implementation/reporting follow-up incomplete | Block |
| 12 ACT-TRN actions | Open | Real training/access/activation readiness absent | Block |
| 12 ACT-VSR actions | Open | Release closure plan established | Maintain hold until approved closure |

NO INFERRED RISK ACCEPTANCE

No closed simulated defect or deviation is interpreted as closure of an Open shared risk. No risk is accepted by inference, by document approval or by a positive test count.

# 8 Operational readiness and handover

| Readiness area | Documented design | Missing effective evidence | State |
| --- | --- | --- | --- |
| Operations and maintenance | OMSOP control model | Approved local process, owners, schedules, records and effectiveness | Not Ready |
| User operation | UG task/safety model | Released site labels, real users, approved access and task qualification | Not Ready |
| Administration | AG controlled-admin model | Released runbooks, privileged roles, independent implementation and production evidence | Not Ready |
| Support/SLA | SLA service/target model | Accepted provider evidence, activated service, monitoring and effective targets | Not Ready |
| Training | TRN curricula, assessments and synthetic records | Real learner assignment, assessment, evidence and access linkage | Not Ready |
| Supplier | Conditional SUPA planning conclusion | Final qualification, responsibilities, service evidence and acceptance | Not Ready |
| Handover | Handover requirements referenced | Ownership acceptance, knowledge transfer, action agreement, hypercare and communication | Not Ready |

HANDOVER HOLD

Operational procedures can be issued as DUMMY design artifacts while the operation itself remains not ready. Handover is deferred and no stakeholder communication may state Release for Use.

# 9 Release decision statements

| Decision ID | Question / decision | Disposition | Controlled meaning |
| --- | --- | --- | --- |
| DEC-VSR-001 | Accept this VSR as a complete DUMMY documentation artifact. | Accept - simulated document approval only | No operational authority |
| DEC-VSR-002 | Determine whether the validated state is established. | No - not established | Evidence is synthetic and release criteria are unmet |
| DEC-VSR-003 | Recommend release for use. | HOLD / DEFER - DO NOT RELEASE | No deployment, activation or stakeholder Release for Use notice |
| DEC-VSR-004 | Determine whether residual risk may be accepted. | No - 26 risks remain Open | No residual ratings or accountable acceptance |
| DEC-VSR-005 | Determine whether operational handover may occur. | No - handover deferred | Ownership, training, support, access and operating evidence are not effective |
| DEC-VSR-006 | Continue the controlled DUMMY documentation plan. | Yes - sequences 30 through 35 remain planned | Maintained-state samples do not retroactively authorise release |

RECOMMENDATION

HOLD / DEFER - DO NOT RELEASE. Re-evaluation requires complete, attributable, independently reviewed and approved evidence for every applicable release criterion and closure action.

# 10 Release blockers

| Blocker | Title | Objective evidence | Gate | Severity |
| --- | --- | --- | --- | --- |
| BLK-VSR-001 | Shared risk population is Open | 26/26 risks have no residual rating or acceptance | G2/G6 | Critical |
| BLK-VSR-002 | Production installation baseline absent | DUMMY verification cannot establish production equivalence or qualification | G4 | Critical |
| BLK-VSR-003 | Cross-package actions remain Open | DUMMY-DRF-MES-007 and ACT-IREP-007 are not closed | G4 | High |
| BLK-VSR-004 | Production change/deployment not executed | No approved production change, as-built deployment record or independent production verification | G4 | Critical |
| BLK-VSR-005 | Training/access readiness not effective | Synthetic cohorts qualify nobody; real role, training, SoD and access evidence absent | G5 | Critical |
| BLK-VSR-006 | Operations/support not activated | SOP, guide, administration and SLA content is DUMMY/proposed; monitoring and support are not effective | G5 | High |
| BLK-VSR-007 | Supplier readiness conditional | Supplier Alpha assessment supports planning only; final service evidence and acceptance absent | G5 | High |
| BLK-VSR-008 | Local procedure/configuration detail Open | Site labels, approved local instructions, endpoint-independent runbooks and released configuration alignment not verified | G5 | High |
| BLK-VSR-009 | Recovery evidence is non-production | Simulated objectives were met, but production rehearsal, authority and reconciliation are absent | G4/G5 | High |
| BLK-VSR-010 | Operational data-integrity governance not demonstrated | Live audit-trail population, review frequency, record retention and control effectiveness are absent | G5 | Critical |
| BLK-VSR-011 | QA release decision absent | No accountable QA release or validated-state approval exists | G6 | Critical |
| BLK-VSR-012 | Handover incomplete | Operational ownership, knowledge transfer, hypercare criteria and acceptance are not evidenced | G6 | High |

Severity ranks decision impact within this DUMMY VSR; it is not a replacement for the shared risk rating model. Every blocker remains Open.

# 11 Closure action plan

| Action | Required closure evidence | Accountable fictional role(s) | Blocker | Due condition | State |
| --- | --- | --- | --- | --- | --- |
| ACT-VSR-001 | Complete mitigation evidence for all 26 risks; assign residual ratings and obtain accountable acceptance. | Risk Owners + Process/System Owners + Quality | BLK-VSR-001 | Before release | Open |
| ACT-VSR-002 | Execute and approve installation verification in the intended production context; establish a reconciled as-built baseline. | Implementation/Verification Leads + Quality | BLK-VSR-002 | Before release | Open |
| ACT-VSR-003 | Close DUMMY-DRF-MES-007 and ACT-IREP-007 with attributable evidence and assess any effect on approved documents. | Assigned Action Owners + Quality | BLK-VSR-003 | Before release | Open |
| ACT-VSR-004 | Approve and execute production change/deployment; independently verify configuration, interfaces and rollback evidence. | Change/Implementation Owners | BLK-VSR-004 | Before release | Open |
| ACT-VSR-005 | Approve real role populations/curricula; complete training and assessments; link to approved least-privilege access and SoD. | Training/Line/Access Owners | BLK-VSR-005 | Before use | Open |
| ACT-VSR-006 | Approve and activate operating, monitoring, incident, maintenance and support processes; make SLA targets effective. | Service/System Owners | BLK-VSR-006 | Before handover | Open |
| ACT-VSR-007 | Complete supplier qualification, responsibilities, service evidence, contractual controls and final acceptance. | Supplier Owner + Quality | BLK-VSR-007 | Before reliance | Open |
| ACT-VSR-008 | Approve site-specific procedures, labels, released configuration references and controlled runbooks. | Process/System Owners + Quality | BLK-VSR-008 | Before use | Open |
| ACT-VSR-009 | Perform an approved production-context recovery rehearsal and document reconciliation and regulated-resume authority. | Recovery/Business/Quality Owners | BLK-VSR-009 | Before release | Open |
| ACT-VSR-010 | Approve operational data-integrity, audit-trail review, retention and effectiveness controls using complete live populations. | Data/Process/System Owners + Quality | BLK-VSR-010 | Before use | Open |
| ACT-VSR-011 | Reissue the release evidence summary after actions close; obtain accountable Quality approval before Release for Use. | Validation Lead + Accountable Quality | BLK-VSR-011 | Final gate | Open |
| ACT-VSR-012 | Complete documented handover, ownership acceptance, knowledge transfer, hypercare criteria and stakeholder communication. | Project/System/Service Owners | BLK-VSR-012 | After release decision | Open |

ACTION CONTROL

All 12 ACT-VSR actions are Open. 'Before release' and similar due conditions prevent invented calendar commitments; accountable owners must assign approved real dates during an authorised implementation.

# 12 Re-evaluation and approval conditions

| Condition | Minimum evidence | Required review | Effect if met |
| --- | --- | --- | --- |
| Baseline integrity | Reconcile approved plan, production as-built configuration and immutable evidence set | Implementation + independent verification | Allows evidence review; not automatic release |
| Requirements/critical aspects | Complete trace to implemented controls and approved production-context verification | Process/System Owners + Quality | Supports fit-for-use conclusion |
| Risk | All risks mitigated; residual ratings assigned; acceptance documented by accountable roles | Risk Owners + Quality | Removes BLK-VSR-001 only |
| Issues/actions | All release-impacting defects, deviations and actions closed or formally dispositioned with approved rationale | Validation Lead + Quality | Removes applicable issue blockers |
| Operational readiness | Real training/access, procedures, support, monitoring, supplier and recovery evidence effective | Operational Owners + Quality | Supports G5 reassessment |
| Handover | Named accountable owners accept documentation, knowledge, open obligations and hypercare criteria | Project/System/Service Owners | Supports G6 handover decision |
| Final Quality decision | Revised VSR/release report concludes fit for intended use with applicable gates met | Accountable Quality | May permit separate Release for Use |

RE-EVALUATION RULE

A future positive recommendation must be issued as a new controlled decision after evidence changes. This v0.1 DUMMY VSR remains a permanent record of the HOLD / DEFER conclusion at its frozen baseline.

# Appendix A - 35-deliverable lifecycle-plan status

| Seq. | Document ID | Deliverable | Status at VSR authoring | VSR relationship |
| --- | --- | --- | --- | --- |
| 1 | NL-MES-MLGP-001 | Master Lifecycle Generation Plan | Issued before VSR | Frozen VSR input |
| 2 | NL-MES-SYS-001 | System Overview and Description | Issued before VSR | Frozen VSR input |
| 3 | NL-MES-IPLAN-001 | IT Implementation Plan | Issued before VSR | Frozen VSR input |
| 4 | NL-MES-URS-001 | User Requirement Specification | Issued before VSR | Frozen VSR input |
| 5 | NL-MES-ITRA-001 | IT Risk Assessment | Issued before VSR | Frozen VSR input |
| 6 | NL-MES-ITRRA-001 | IT Requirement Risk Assessment | Issued before VSR | Frozen VSR input |
| 7 | NL-MES-SUPA-001 | Supplier Assessment Report | Issued before VSR | Frozen VSR input |
| 8 | NL-MES-FS-001 | Functional Specification | Issued before VSR | Frozen VSR input |
| 9 | NL-MES-IS-001 | Integration Specification | Issued before VSR | Frozen VSR input |
| 10 | NL-MES-DS-001 | Design Specification | Issued before VSR | Frozen VSR input |
| 11 | NL-MES-CS-001 | Configuration Specification | Issued before VSR | Frozen VSR input |
| 12 | NL-MES-DIA-001 | Data Integrity Assessment | Issued before VSR | Frozen VSR input |
| 13 | NL-MES-DRR-001 | Design Review Report | Issued before VSR | Frozen VSR input |
| 14 | NL-MES-TRM-001 | Traceability Matrix | Issued before VSR | Frozen VSR input |
| 15 | NL-MES-IQP-001 | Installation Qualification Protocol | Issued before VSR | Frozen VSR input |
| 16 | NL-MES-IQTC-001 | IQ Test Cases | Issued before VSR | Frozen VSR input |
| 17 | NL-MES-DEFL-001 | Defect Log | Issued before VSR | Frozen VSR input |
| 18 | NL-MES-DEVL-001 | Deviation Log | Issued before VSR | Frozen VSR input |
| 19 | NL-MES-IQR-001 | IQ Report | Issued before VSR | Frozen VSR input |
| 20 | NL-MES-BRVR-001 | Backup and Restore Verification Report | Issued before VSR | Frozen VSR input |
| 21 | NL-MES-IRP-001 | IT Recovery Plan | Issued before VSR | Frozen VSR input |
| 22 | NL-MES-IRTR-001 | IT Recovery Test Protocol and Report | Issued before VSR | Frozen VSR input |
| 23 | NL-MES-IREP-001 | IT Implementation Report | Issued before VSR | Frozen VSR input |
| 24 | NL-MES-OMSOP-001 | Operation and Maintenance SOP | Issued before VSR | Frozen VSR input |
| 25 | NL-MES-UG-001 | User Guide | Issued before VSR | Frozen VSR input |
| 26 | NL-MES-AG-001 | Administrator Guide | Issued before VSR | Frozen VSR input |
| 27 | NL-MES-SLA-001 | Service Level Agreement | Issued before VSR | Frozen VSR input |
| 28 | NL-MES-TRN-001 | Training Matrix and Training Evidence Index | Issued before VSR | Frozen VSR input |
| 29 | NL-MES-VSR-001 | Final Validation Summary Report / Release Recommendation | Current VSR - simulated approved / HOLD | Decision document |
| 30 | NL-MES-CHG-001 | Change Record Pack | Planned after VSR | Maintained-state sample; not pre-release evidence by plan sequence |
| 31 | NL-MES-INC-001 | Incident Sample Pack | Planned after VSR | Maintained-state sample; not pre-release evidence by plan sequence |
| 32 | NL-MES-ATR-001 | Audit Trail Review SOP or Report | Planned after VSR | Maintained-state sample; not pre-release evidence by plan sequence |
| 33 | NL-MES-AMRR-001 | Access Management Review Report | Planned after VSR | Maintained-state sample; not pre-release evidence by plan sequence |
| 34 | NL-MES-ITPSE-001 | IT Periodic System Evaluation Report | Planned after VSR | Maintained-state sample; not pre-release evidence by plan sequence |
| 35 | NL-MES-URR-001 | User Requirement Review Report | Planned after VSR | Maintained-state sample; not pre-release evidence by plan sequence |

PACKAGE COMPLETION BOUNDARY

The VSR is sequence 29, not the final document in the 35-item user package. Sequences 30-35 remain required after this delivery. Their planned maintained-state sample status does not make them evidence of an already released system.

# Appendix B - 28-document immutable input baseline

| Seq. | Document ID | Filename | SHA-256 | Bytes |
| --- | --- | --- | --- | --- |
| 1 | NL-MES-MLGP-001 | NOVOLIFE-MES-MLGP-Master Lifecycle Generation Plan-v0.1-DUMMY.docx | 58DF06F0CFDD20FDAE47DB054D62B66DA640576CDCD2B14132502E6C60277453 | 64240 |
| 2 | NL-MES-SYS-001 | NOVOLIFE-MES-SYS-System Overview and Description-v0.1-DUMMY.docx | 0C2D6C7F6CA960538A78DD91DB130ECA9384B1A251458700B2AABEB71B94E987 | 60205 |
| 3 | NL-MES-IPLAN-001 | NOVOLIFE-MES-IPLAN-IT Implementation Plan-v0.1-DUMMY.docx | B285EC5379FB80AE89CE087756E096B4D678A029BCDCF7521F8C07C2465AB1C9 | 65078 |
| 4 | NL-MES-URS-001 | NOVOLIFE-MES-URS-User Requirement Specification-v0.1-DUMMY.docx | FC480E613AF60A29C59B293EC7F0F42D14C1ECA3B1C8D7A3E63C372D78C6B856 | 88124 |
| 5 | NL-MES-ITRA-001 | NOVOLIFE-MES-ITRA-IT Risk Assessment-v0.1-DUMMY.docx | 6D91B4D8B1EB9771FC767987AC42AB1E68E548B880F9071EE9522837285B5798 | 82700 |
| 6 | NL-MES-ITRRA-001 | NOVOLIFE-MES-ITRRA-IT Requirement Risk Assessment-v0.1-DUMMY.docx | A63BC70EB0BA184AF0544DE78C18DBFBCE00585F3BD2B25FAA6AF478BB42BEAF | 89244 |
| 7 | NL-MES-SUPA-001 | NOVOLIFE-MES-SUPA-Supplier Assessment Report-v0.1-DUMMY.docx | DF2BD6401E9105CE5DC9EC28E9D2D60F3776E2B7A3852D06D6368B12AE2C8BDA | 67356 |
| 8 | NL-MES-FS-001 | NOVOLIFE-MES-FS-Functional Specification-v0.1-DUMMY.docx | 8E40D5921E7A77A8BF15C263D5F7DB692DC4CD397339D2BB14B6F647872B9618 | 77007 |
| 9 | NL-MES-IS-001 | NOVOLIFE-MES-IS-Integration Specification-v0.1-DUMMY.docx | E7E96103779203A8E8652B119C04C0F7D6860F05E3173173029DD880C81DE32F | 90712 |
| 10 | NL-MES-DS-001 | NOVOLIFE-MES-DS-Design Specification-v0.1-DUMMY.docx | E1A8E41194D607D8ADB8B042B8D2AD29A587D7FC24E26D34A20AB19560B79392 | 90588 |
| 11 | NL-MES-CS-001 | NOVOLIFE-MES-CS-Configuration Specification-v0.1-DUMMY.docx | 8F4078E36FED3D3A523A0A4BB565E9BBCCF1DFF32112E53BCA6EE4ECE1EA97FC | 91307 |
| 12 | NL-MES-DIA-001 | NOVOLIFE-MES-DIA-Data Integrity Assessment-v0.1-DUMMY.docx | B796EC45FE517BA95C9722CE28D96B6D791586CFDEFD489E2714F7D093102DC8 | 94744 |
| 13 | NL-MES-DRR-001 | NOVOLIFE-MES-DRR-Design Review Report-v0.1-DUMMY.docx | B813A6952F062902386D0167B1EC80D035B4480B878978B82796319A515D0B4C | 75977 |
| 14 | NL-MES-TRM-001 | NOVOLIFE-MES-TRM-Traceability Matrix-v0.1-DUMMY.docx | 9081D1DB2E675AE7EA2F86FA31B4717EFD4A664674BC4DA5992A6CCB79DDAFBC | 85691 |
| 15 | NL-MES-IQP-001 | NOVOLIFE-MES-IQP-Installation Qualification Protocol-v0.1-DUMMY.docx | 41EB6086AA6F424BFEEDE6AEFD5872049AB84281A16B5329D97AD8E5CF9ECA68 | 79587 |
| 16 | NL-MES-IQTC-001 | NOVOLIFE-MES-IQTC-IQ Test Cases-v0.1-DUMMY.docx | FB142153117CF0CC9A684951363E74D74D82B09C525ABF8045E16309163B6029 | 182285 |
| 17 | NL-MES-DEFL-001 | NOVOLIFE-MES-DEFL-Defect Log-v0.1-DUMMY.docx | BDB8CF30C89EF0904F5CBA509AE908318F03C7D70EE70A8F9B90898AD3743E75 | 79930 |
| 18 | NL-MES-DEVL-001 | NOVOLIFE-MES-DEVL-Deviation Log-v0.1-DUMMY.docx | 7D03DCD025F3838D49E612C5D75F2980AFF066579E84C530CE6B984036FE5DCF | 74298 |
| 19 | NL-MES-IQR-001 | NOVOLIFE-MES-IQR-IQ Report-v0.1-DUMMY.docx | 4B329CEC3B474FC3F35DBD60CDFD4FCC6654502CFB3894A1BD59261F3A2BDA67 | 68428 |
| 20 | NL-MES-BRVR-001 | NOVOLIFE-MES-BRVR-Backup and Restore Verification Report-v0.1-DUMMY.docx | EA7C6009C110DD5F4C8C01C393FD654DE1527C3AB5AA7727AE2F86F87B795DE9 | 64804 |
| 21 | NL-MES-IRP-001 | NOVOLIFE-MES-IRP-IT Recovery Plan-v0.1-DUMMY.docx | D1214D7E47B8BEBB13AC8417D8E7C6E8D78DDA345B6E9232767ED2BFF28D91C6 | 79870 |
| 22 | NL-MES-IRTR-001 | NOVOLIFE-MES-IRTR-IT Recovery Test Protocol and Report-v0.1-DUMMY.docx | E33969B33885D400CEBD5EA28486E0E8738BF5C897BA68B9FD6FB84CC4696E79 | 81110 |
| 23 | NL-MES-IREP-001 | NOVOLIFE-MES-IREP-IT Implementation Report-v0.1-DUMMY.docx | 61463A7ECFB07ADBF2E7FE870AAB6A9CFDF75E32B9B28E6FB940A38ED3C64081 | 76373 |
| 24 | NL-MES-OMSOP-001 | NOVOLIFE-MES-OMSOP-Operation and Maintenance SOP-v0.1-DUMMY.docx | 44F096E8E7A0A7DE27CB647AEE814E647B78B0E9E3EE379BDAE3ED810281DE30 | 87196 |
| 25 | NL-MES-UG-001 | NOVOLIFE-MES-UG-User Guide-v0.1-DUMMY.docx | 0A297A7AF26CD1B310BD106946D952853EF5596C803F1CEC96BDCDD64E081ECA | 74776 |
| 26 | NL-MES-AG-001 | NOVOLIFE-MES-AG-Administrator Guide-v0.1-DUMMY.docx | B8A8F315B3DFF3602287195F1B20515B20E16C671A920A54B6367B65F8B63CAC | 79571 |
| 27 | NL-MES-SLA-001 | NOVOLIFE-MES-SLA-Service Level Agreement-v0.1-DUMMY.docx | 4CEB197383707739D5925B0E79E0E8E99F9E02681DE3B2850B941F9A2CE85A7F | 71800 |
| 28 | NL-MES-TRN-001 | NOVOLIFE-MES-TRN-Training Matrix and Training Evidence Index-v0.1-DUMMY.docx | 118006D4922DDEB0D632272644F6D8999A0FC84B29237526F56504EF33B6A166 | 81438 |

Hash values identify the exact files evaluated. A change to any source after this freeze requires impact assessment and VSR re-evaluation.

# Appendix C - 50-URS release trace

| Requirement | Statement | Evidence domain | Primary sources | VSR evidence conclusion | Release disposition |
| --- | --- | --- | --- | --- | --- |
| URS-MES-001 | Approved order and instruction selection | EVID-VSR-002/005/007 | URS; FS; DS; CS; TRM; IQR | DUMMY requirements/design/IQ chain present; production effectiveness not demonstrated | HOLD - production evidence absent |
| URS-MES-002 | Controlled execution sequence | EVID-VSR-002/005/007 | URS; FS; DS; CS; TRM; IQR | DUMMY requirements/design/IQ chain present; production effectiveness not demonstrated | HOLD - production evidence absent |
| URS-MES-003 | Execution data and calculation capture | EVID-VSR-002/005/007 | URS; FS; DS; CS; TRM; IQR | DUMMY requirements/design/IQ chain present; production effectiveness not demonstrated | HOLD - production evidence absent |
| URS-MES-004 | Material and equipment status verification | EVID-VSR-002/005/007 | URS; FS; DS; CS; TRM; IQR | DUMMY requirements/design/IQ chain present; production effectiveness not demonstrated | HOLD - production evidence absent |
| URS-MES-005 | Controlled hold, resume, and termination | EVID-VSR-002/005/007 | URS; FS; DS; CS; TRM; IQR | DUMMY requirements/design/IQ chain present; production effectiveness not demonstrated | HOLD - production evidence absent |
| URS-MES-006 | Exception and review-by-exception handling | EVID-VSR-002/005/007 | URS; FS; DS; CS; TRM; IQR | DUMMY requirements/design/IQ chain present; production effectiveness not demonstrated | HOLD - production evidence absent |
| URS-MES-007 | Complete electronic batch record | EVID-VSR-002/005/007 | URS; FS; DS; CS; TRM; IQR | DUMMY requirements/design/IQ chain present; production effectiveness not demonstrated | HOLD - production evidence absent |
| URS-MES-008 | Batch-record completion control | EVID-VSR-002/005/007 | URS; FS; DS; CS; TRM; IQR | DUMMY requirements/design/IQ chain present; production effectiveness not demonstrated | HOLD - production evidence absent |
| URS-MES-009 | Authorised batch-record review | EVID-VSR-002/005/007 | URS; FS; DS; CS; TRM; IQR | DUMMY requirements/design/IQ chain present; production effectiveness not demonstrated | HOLD - production evidence absent |
| URS-MES-010 | Record retention and retrieval | EVID-VSR-002/005/007 | URS; FS; DS; CS; TRM; IQR | DUMMY requirements/design/IQ chain present; production effectiveness not demonstrated | HOLD - production evidence absent |
| URS-MES-011 | Complete and accurate record copies | EVID-VSR-002/005/007 | URS; FS; DS; CS; TRM; IQR | DUMMY requirements/design/IQ chain present; production effectiveness not demonstrated | HOLD - production evidence absent |
| URS-MES-012 | Unique identity and authentication | EVID-VSR-003/010/011 | URS; ITRA; ITRRA; DS; CS; TRN; AG | Access design/training model present; real identity, role and SoD evidence absent | HOLD - production evidence absent |
| URS-MES-013 | Role-based least-privilege access | EVID-VSR-003/010/011 | URS; ITRA; ITRRA; DS; CS; TRN; AG | Access design/training model present; real identity, role and SoD evidence absent | HOLD - production evidence absent |
| URS-MES-014 | Controlled access lifecycle | EVID-VSR-003/010/011 | URS; ITRA; ITRRA; DS; CS; TRN; AG | Access design/training model present; real identity, role and SoD evidence absent | HOLD - production evidence absent |
| URS-MES-015 | Privileged and service-account control | EVID-VSR-003/010/011 | URS; ITRA; ITRRA; DS; CS; TRN; AG | Access design/training model present; real identity, role and SoD evidence absent | HOLD - production evidence absent |
| URS-MES-016 | Segregation and periodic access review | EVID-VSR-003/010/011 | URS; ITRA; ITRRA; DS; CS; TRN; AG | Access design/training model present; real identity, role and SoD evidence absent | HOLD - production evidence absent |
| URS-MES-017 | Authorised electronic-signature application | EVID-VSR-003/005/007 | URS; FS; DS; DIA; IQR | Electronic-signature controls traced in simulation; live attribution not verified | HOLD - production evidence absent |
| URS-MES-018 | Signature meaning and content | EVID-VSR-003/005/007 | URS; FS; DS; DIA; IQR | Electronic-signature controls traced in simulation; live attribution not verified | HOLD - production evidence absent |
| URS-MES-019 | Permanent signature-to-record linkage | EVID-VSR-003/005/007 | URS; FS; DS; DIA; IQR | Electronic-signature controls traced in simulation; live attribution not verified | HOLD - production evidence absent |
| URS-MES-020 | Automatic audit-trail capture | EVID-VSR-003/005/010 | URS; DIA; DS; OMSOP; UG; AG | Audit-trail design/review model present; operational population and effectiveness absent | HOLD - production evidence absent |
| URS-MES-021 | Audit-trail protection and retention | EVID-VSR-003/005/010 | URS; DIA; DS; OMSOP; UG; AG | Audit-trail design/review model present; operational population and effectiveness absent | HOLD - production evidence absent |
| URS-MES-022 | Audit-trail search and review presentation | EVID-VSR-003/005/010 | URS; DIA; DS; OMSOP; UG; AG | Audit-trail design/review model present; operational population and effectiveness absent | HOLD - production evidence absent |
| URS-MES-023 | Risk-based audit-trail review evidence | EVID-VSR-003/005/010 | URS; DIA; DS; OMSOP; UG; AG | Audit-trail design/review model present; operational population and effectiveness absent | HOLD - production evidence absent |
| URS-MES-024 | ALCOA+ data lifecycle | EVID-VSR-003/005/010 | URS; DIA; DRR; OMSOP | Data-integrity controls documented; live record lifecycle not demonstrated | HOLD - production evidence absent |
| URS-MES-025 | Authoritative and consistent time | EVID-VSR-003/005/010 | URS; DIA; DRR; OMSOP | Data-integrity controls documented; live record lifecycle not demonstrated | HOLD - production evidence absent |
| URS-MES-026 | Controlled correction of GxP data | EVID-VSR-003/005/010 | URS; DIA; DRR; OMSOP | Data-integrity controls documented; live record lifecycle not demonstrated | HOLD - production evidence absent |
| URS-MES-027 | Preservation through transfer, retention, and migration | EVID-VSR-003/005/010 | URS; DIA; DRR; OMSOP | Data-integrity controls documented; live record lifecycle not demonstrated | HOLD - production evidence absent |
| URS-MES-028 | ERP inbound orders and master data | EVID-VSR-005/006/007 | URS; IS; DS; CS; TRM; IQR | Interfaces traced and simulated; production endpoints, reconciliation and load not verified | HOLD - production evidence absent |
| URS-MES-029 | ERP outbound manufacturing confirmation | EVID-VSR-005/006/007 | URS; IS; DS; CS; TRM; IQR | Interfaces traced and simulated; production endpoints, reconciliation and load not verified | HOLD - production evidence absent |
| URS-MES-030 | LIMS sample request and status transfer | EVID-VSR-005/006/007 | URS; IS; DS; CS; TRM; IQR | Interfaces traced and simulated; production endpoints, reconciliation and load not verified | HOLD - production evidence absent |
| URS-MES-031 | LIMS result and disposition receipt | EVID-VSR-005/006/007 | URS; IS; DS; CS; TRM; IQR | Interfaces traced and simulated; production endpoints, reconciliation and load not verified | HOLD - production evidence absent |
| URS-MES-032 | Controlled commands to automation | EVID-VSR-005/006/007 | URS; IS; DS; CS; TRM; IQR | Interfaces traced and simulated; production endpoints, reconciliation and load not verified | HOLD - production evidence absent |
| URS-MES-033 | Automation data receipt | EVID-VSR-005/006/007 | URS; IS; DS; CS; TRM; IQR | Interfaces traced and simulated; production endpoints, reconciliation and load not verified | HOLD - production evidence absent |
| URS-MES-034 | Historian and reporting publication | EVID-VSR-005/006/007 | URS; IS; DS; CS; TRM; IQR | Interfaces traced and simulated; production endpoints, reconciliation and load not verified | HOLD - production evidence absent |
| URS-MES-035 | Enterprise identity integration | EVID-VSR-005/006/007 | URS; IS; DS; CS; TRM; IQR | Interfaces traced and simulated; production endpoints, reconciliation and load not verified | HOLD - production evidence absent |
| URS-MES-036 | Common interface integrity and failure control | EVID-VSR-005/006/007 | URS; IS; DS; CS; TRM; IQR | Interfaces traced and simulated; production endpoints, reconciliation and load not verified | HOLD - production evidence absent |
| URS-MES-037 | Risk-based backup coverage | EVID-VSR-008 | URS; BRVR; IRP; IRTR | Simulated recovery objectives met; production rehearsal and resume authority absent | HOLD - production evidence absent |
| URS-MES-038 | Complete and accurate restoration | EVID-VSR-008 | URS; BRVR; IRP; IRTR | Simulated recovery objectives met; production rehearsal and resume authority absent | HOLD - production evidence absent |
| URS-MES-039 | Coordinated service recovery | EVID-VSR-008 | URS; BRVR; IRP; IRTR | Simulated recovery objectives met; production rehearsal and resume authority absent | HOLD - production evidence absent |
| URS-MES-040 | Backup and recovery verification and monitoring | EVID-VSR-008 | URS; BRVR; IRP; IRTR | Simulated recovery objectives met; production rehearsal and resume authority absent | HOLD - production evidence absent |
| URS-MES-041 | Operational execution reporting | EVID-VSR-002/003/010 | URS; DIA; UG; OMSOP | Reporting/review controls documented; operational provenance and review effectiveness absent | HOLD - production evidence absent |
| URS-MES-042 | Quality and review-by-exception reporting | EVID-VSR-002/003/010 | URS; DIA; UG; OMSOP | Reporting/review controls documented; operational provenance and review effectiveness absent | HOLD - production evidence absent |
| URS-MES-043 | Interface and exception reconciliation reporting | EVID-VSR-002/003/010 | URS; DIA; UG; OMSOP | Reporting/review controls documented; operational provenance and review effectiveness absent | HOLD - production evidence absent |
| URS-MES-044 | Controlled report and extract provenance | EVID-VSR-002/003/010 | URS; DIA; UG; OMSOP | Reporting/review controls documented; operational provenance and review effectiveness absent | HOLD - production evidence absent |
| URS-MES-045 | Operational monitoring and alerting | EVID-VSR-010 | URS; OMSOP; AG; SLA | Monitoring design exists; service is not activated or demonstrated | HOLD - production evidence absent |
| URS-MES-046 | Incident and problem control | EVID-VSR-010 | URS; OMSOP; AG; SLA | Incident workflow is defined; operational support and targets are not effective | HOLD - production evidence absent |
| URS-MES-047 | Controlled change and configuration baseline | EVID-VSR-005/009/010 | URS; CS; IREP; OMSOP; AG | Infrastructure/operation controls documented; production baseline and operation absent | HOLD - production evidence absent |
| URS-MES-048 | Supplier and service-provider assurance | EVID-VSR-005/009/010 | URS; CS; IREP; OMSOP; AG | Infrastructure/operation controls documented; production baseline and operation absent | HOLD - production evidence absent |
| URS-MES-049 | Periodic evaluation of continued fitness | EVID-VSR-005/009/010 | URS; CS; IREP; OMSOP; AG | Infrastructure/operation controls documented; production baseline and operation absent | HOLD - production evidence absent |
| URS-MES-050 | Role-based training and controlled guidance | EVID-VSR-005/009/010 | URS; CS; IREP; OMSOP; AG | Infrastructure/operation controls documented; production baseline and operation absent | HOLD - production evidence absent |

URS TRACE CONCLUSION

50 of 50 URS requirements are represented. Population completeness is not a release result: each requirement remains bounded by absent production implementation/effectiveness evidence and the package-wide HOLD.

# Appendix D - 26-risk release trace

| Risk | Scenario | Evidence domain | Primary sources | State | Residual / acceptance | Release disposition |
| --- | --- | --- | --- | --- | --- | --- |
| RSK-MES-001 | Unapproved order, recipe, or execution state | EVID-VSR-003/005/010 | DIA; DS; OMSOP | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-002 | Incorrect or incomplete execution data and calculations | EVID-VSR-003/005/010 | DIA; DS; OMSOP | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-003 | Incomplete batch completion, exception disposition, or review | EVID-VSR-003/005/010 | DIA; DS; OMSOP | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-004 | Loss, unreadability, or incomplete copy of regulated records | EVID-VSR-003/005/010 | DIA; DS; OMSOP | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-005 | Unauthorised or excessive access | EVID-VSR-003/010/011 | ITRRA; DS; AG; TRN | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-006 | Credential, session, or service-account compromise | EVID-VSR-003/010/011 | ITRRA; DS; AG; TRN | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-007 | Invalid or non-attributable electronic signature | EVID-VSR-003/010/011 | ITRRA; DS; AG; TRN | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-008 | Incomplete, alterable, or ineffective audit trail | EVID-VSR-003/010/011 | ITRRA; DS; AG; TRN | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-009 | Inconsistent time and chronology | EVID-VSR-005/006/007 | IS; DS; TRM; IQR | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-010 | Uncontrolled correction, deletion, or record lifecycle | EVID-VSR-005/006/007 | IS; DS; TRM; IQR | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-011 | ERP order/master-data or confirmation interface failure | EVID-VSR-005/006/007 | IS; DS; TRM; IQR | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-012 | LIMS sample, result, or disposition interface failure | EVID-VSR-005/006/007 | IS; DS; TRM; IQR | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-013 | Automation command, state, or measurement mismatch | EVID-VSR-005/008/010 | CS; BRVR; IRP; IRTR; OMSOP | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-014 | Historian/reporting publication is incomplete or misleading | EVID-VSR-005/008/010 | CS; BRVR; IRP; IRTR; OMSOP | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-015 | Cross-interface integrity, monitoring, or reconciliation failure | EVID-VSR-005/008/010 | CS; BRVR; IRP; IRTR; OMSOP | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-016 | Application or infrastructure unavailability and capacity exhaustion | EVID-VSR-005/008/010 | CS; BRVR; IRP; IRTR; OMSOP | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-017 | Backup is incomplete, corrupt, unavailable, or outside need | EVID-VSR-005/007/009 | CS; IQR; IREP; AG | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-018 | Recovery fails objectives or creates inconsistent state | EVID-VSR-005/007/009 | CS; IQR; IREP; AG | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-019 | Cyber vulnerability, malware, or insecure component | EVID-VSR-005/007/009 | CS; IQR; IREP; AG | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-020 | Supplier or shared-service controls are unclear or ineffective | EVID-VSR-005/007/009 | CS; IQR; IREP; AG | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-021 | Uncontrolled change, configuration, or promotion | EVID-VSR-003/004/010 | SUPA; SLA; OMSOP | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-022 | Incident or problem handling fails to protect GxP state | EVID-VSR-003/004/010 | SUPA; SLA; OMSOP | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-023 | Controlled report or extract is misinterpreted or altered | EVID-VSR-003/004/010 | SUPA; SLA; OMSOP | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-024 | Maintained-state controls, review, or training become ineffective | EVID-VSR-003/008/010 | DIA; IRTR; OMSOP; AG | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-025 | Personal data processing is excessive or insufficiently protected | EVID-VSR-003/008/010 | DIA; IRTR; OMSOP; AG | Open | None / not accepted | BLK-VSR-001; HOLD |
| RSK-MES-026 | Initial load or migration loses content and meaning | EVID-VSR-003/008/010 | DIA; IRTR; OMSOP; AG | Open | None / not accepted | BLK-VSR-001; HOLD |

RISK TRACE CONCLUSION

All 26 shared risks remain Open. The VSR assigns no residual rating, records no acceptance and authorises no risk-based release.

# Appendix E - Source/guidance register and quality gate

## E1 Controlled source register

| Source | Version/status | Use in VSR | Boundary |
| --- | --- | --- | --- |
| Q0715589 | v1.0 Approved | Acceptance verification, release readiness and reporting criteria | Guidance; project-specific applicability assessed |
| Q218515 | v8.0 Effective | Risk-based validation and validated-state conclusion | Procedure criteria applied conservatively |
| Q0300381 | v5.0 Effective | Validation discrepancy classification and disposition | No real deviation record created |
| Q0359333 | v2.0 Approved | Handover documentation, knowledge and action readiness | Checklist does not replace lifecycle deliverables |
| Q187219 | v12.0 | IT lifecycle accountability and release boundary | Source-controlled instruction |
| Q0359339 | v4.0 | Controlled documentation and retained-format decision | No dedicated VSR template found |
| Q0359350 | v2.0 | Implementation report/result/open-action structure | Applied as report design guidance |

## E2 VSR quality gate

| Gate | Check | Evidence | Result |
| --- | --- | --- | --- |
| VSR-QG-01 | Identification | NL-MES-VSR-001; v0.1; 12 Aug 2026; exact DUMMY status/footer | Pass |
| VSR-QG-02 | Decision clarity | HOLD / DEFER - DO NOT RELEASE; validated state not established | Pass |
| VSR-QG-03 | Gate integrity | G0/G1 Met; G2/G3 Scoped Met; G4/G5/G6 Not Met | Pass |
| VSR-QG-04 | Populations | 7 gates; 6 decisions; 12 evidence domains; 12 blockers; 12 actions | Pass |
| VSR-QG-05 | Traceability | 50/50 URS and 26/26 risks; all risks Open/no residual acceptance | Pass |
| VSR-QG-06 | Source freeze | 28/28 issued input documents with filename, bytes and SHA-256 | Pass |
| VSR-QG-07 | Evidence boundary | Simulated results retained without production equivalence/qualification claim | Pass |
| VSR-QG-08 | Open-state integrity | DUMMY-DRF-MES-007, ACT-IREP-007, 12 ACT-TRN and 12 ACT-VSR Open | Pass |
| VSR-QG-09 | Package scope | 35 deliverables reconciled; sequences 30-35 remain planned | Pass |
| VSR-QG-10 | Privacy/security | No real names/signatures/emails/phones/URLs/secrets/endpoints/production IDs | Pass |
| VSR-QG-11 | Template/package | MLGP styles/numbering/theme/footer/font/web-settings retained byte-identically | Pass |
| VSR-QG-12 | Render/delivery | Every page visually inspected; delivered byte/page/pixel equality required | Pass after delivery verification |

FINAL STATUS

Simulated Reviewed and Approved for Demo/Training Use Only. The VSR is complete only as a DUMMY validation-summary artifact. Release remains HOLD / DEFER. No validated state, production qualification, risk acceptance, deployment, access, operation, handover or GxP release is claimed or authorised.